## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Material Requisition To Resource Division |  |  | RTOR000497/2023-2024 | 3057/1/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 17.17 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Quotation Bill for New Service Connection at Madhabpur W/S. Sch. TW-I |  |  | BILL/04165/2023-2024 | 399 | 09/11/2023 | 09/11/2023 | WBSEDCL | 3.86 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Quotation for new service connection charge at Madhabpur PWSS, TW - II |  |  | BILL/04371/2023-2024 | 463 | 01/12/2023 | 01/12/2023 | WBSEDCL | 8.57 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Hiring of Luxury Car (BS-IV) for the Official use of the Executive Engineer, Electrical Division, PHE Dte. w.e.f. 01.12.2023 to 31.05.2024. | Assistant Engineer 1 | Junior Engineer5 | ORD/001947/2023-2024 | 876/AE-I/ED | 23/11/2023 | 23/05/2024 | TRIDIP SARKAR | 0.87 | 2.4 | 275.53 | 10
5 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SELALPUR (2Nos.), MADHABPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000234/2024-2025 | 3469/HUG | 04/10/2024 | 02/01/2025 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 47.22 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MADHABPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000134/2024-2025 | 1159/ED | 14/06/2024 | 12/09/2024 | SANKAR PRASAD DUTTA & CO. | 10.91 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Sinking of 2 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Siteof MADHABPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte |  |  | ORD/000256/2024-2025 | 3526/HUG | 22/10/2024 | 21/11/2024 | GITA ENTERPRISE | 31.35 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 31/10/2025 | S & P ENTERPRISE | 2296.42 | 294.27 | 12.81 | 30
9 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Horizontal Auger boring with water jet system & other ancillary works at Madhabpur Water Suply Scheme under Serampur Sub Division of Hooghly Division PHE Dte, |  |  | ORD/001837/2024-2025 | 333/HUG | 05/02/2025 | 06/04/2025 | ARUN SEAL AND CO. | 28.35 | 0 | 0 | 0
Total | [13 empty] | 2444.71 | 296.67 | 12.14