## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Madhabpur water supply scheme, T.W. No.- I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000812/2023-2024 | 3157/ED | 27/07/2023 | 25/10/2023 | RAJIB COMPANY | 21.49 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Material Requisition To Resource Division |  |  | RTOR000497/2023-2024 | 3057/1/Hug | 11/10/2023 |  | Resource Division | 17.17 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Quotation Bill for New Service Connection at Madhabpur W/S. Sch. TW-I |  |  | BILL/04165/2023-2024 | 399 | 09/11/2023 |  | WBSEDCL | 3.86 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Quotation for new service connection charge at Madhabpur PWSS, TW - II |  |  | BILL/04371/2023-2024 | 463 | 01/12/2023 |  | WBSEDCL | 8.57 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Quotation for new service connection charge at Madhabpur PWSS, TW - II |  |  | BILL/04371/2023-2024 | 463 | 01/12/2023 |  | WBSEDCL | 8.57 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Hiring of Luxury Car (BS-IV) for the Official use of the Executive Engineer, Electrical Division, PHE Dte. w.e.f. 01.12.2023 to 31.05.2024. | Assistant Engineer 1 | Junior Engineer5 | ORD/001947/2023-2024 | 876/AE-I/ED | 23/11/2023 | 21/05/2024 | TRIDIP SARKAR | 0.87 | 1.6 | 183.7 | 10
7 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MADHABPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000134/2024-2025 | 1159/ED | 14/06/2024 | 12/09/2024 | SANKAR PRASAD DUTTA & CO. | 10.91 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MADHABPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18288 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 25/10/2024 | S & P ENTERPRISE | 2296.42 | 46.16 | 2.01 | 30
Total | [13 empty] | 2367.84 | 47.76 | 2.02