## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Material Requisition To Resource Division |  |  | RTOR000435/2023-2024 | 3057/32/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.03 | 0 | 0 | 0
2 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Material Requisition To Resource Division |  |  | RTOR000549/2023-2024 | 3616/Hug | 06/12/2023 | 06/12/2023 | Resource Division | 20.86 | 0 | 0 | 0
3 | HOOGHLY | Goghat-I | Electrical | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Quotation Bill for New Service Connection at Kumursha W/S. Sch. |  |  | BILL/04410/2023-2024 | 488 | 06/12/2023 | 06/12/2023 | WBSEDCL | 4.16 | 0 | 0 | 0
4 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for KUMURSA Piped Water Supply Scheme underARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000244/2024-2025 | 3463/HUG | 04/10/2024 | 03/12/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 53.64 | 0 | 0 | 0
5 | HOOGHLY | Goghat-I | Electrical | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Quotation of New Service Connection for Kumursa w/s Scheme,PH No-II Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18307) Application No-5004423612 Reference Id-503761600 |  |  | BILL/02034/2024-2025 | 513 | 21/10/2024 | 21/10/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
6 | HOOGHLY | Goghat-I | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SELALPUR PWSS - 4no's (2) TIROL PWSS (Z-I)- 4 no's (3) KUMURSA PWSS- 2no's (4) MADHABPUR PWSS- 4no's | Assistant Engineer | Junior Engineer (Civill) | ORD/002743/2024-2025 | 1151/Arg | 10/12/2024 | 10/01/2025 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 0
7 | HOOGHLY | Goghat-I | Electrical | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumursa water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000811/2023-2024 | 3156/ED | 27/07/2023 | 01/03/2025 | ANJAN ENTERPRISE | 21.46 | 0 | 0 | 50
Total | [13 empty] | 122.18 | 0 | 0