## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumursa water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000811/2023-2024 | 3156/ED | 27/07/2023 | 25/10/2023 | ANJAN ENTERPRISE | 21.46 | 0 | 0 | 0
2 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Material Requisition To Resource Division |  |  | RTOR000435/2023-2024 | 3057/32/Hug | 11/10/2023 |  | Resource Division | 15.03 | 0 | 0 | 0
3 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Quotation Bill for New Service Connection at Kumursha W/S. Sch. |  |  | BILL/04410/2023-2024 | 488 | 06/12/2023 |  | WBSEDCL | 4.16 | 0 | 0 | 0
4 | HOOGHLY | Goghat - I | Electrical | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | Quotation Bill for New Service Connection at Kumursha W/S. Sch. |  |  | BILL/04410/2023-2024 | 488 | 06/12/2023 |  | WBSEDCL | 4.16 | 0 | 0 | 0
5 | HOOGHLY | Goghat - I | Hooghly Division | GROUND WATER BASED KUMURSA PIPED WATER SUPPLY SCHEME IN GOGHAT-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18307 | New | KUMURSA Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-I Block, District:-Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000259/2023-2024 | 2213/Hug | 28/07/2023 | 22/07/2024 | P.B. ENTERPRISE (PINTU BHADURI) | 660.63 | 266.68 | 40.37 | 67
Total | [13 empty] | 705.43 | 266.68 | 37.8