## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Udaypur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000817/2023-2024 | 3162/ED | 27/07/2023 | 25/10/2023 | DEBJYOTI BASU | 21.36 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Material Requisition To Resource Division |  |  | RTOR000391/2023-2024 | 3057/56/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.7 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at MAHISHGOT ZONE I (2Nos.), UDAYPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000227/2024-2025 | 3437/HUG | 03/10/2024 | 01/01/2025 | SAHA CONSTRUCTION AND CO | 47.26 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036968/Quot/03 Reference ID- 503576706 SM Code- 18308 |  |  | BILL/06216/2023-2024 | 819 | 01/03/2024 | 01/03/2024 | WBSEDCL | 11.54 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Quotation money deposition for new service connection at udaypur w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037021/Quot/03 Reference ID- 503576711 SM Code- 18308 |  |  | BILL/06215/2023-2024 | 818 | 03/03/2024 | 03/03/2024 | WBSEDCL | 3.92 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 01/04/2026 | MACKINTOSH BURN LIMITED | 3480.01 | 258.22 | 7.42 | 45
7 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Sinking of 2 nos 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed T/W Site of UDAYPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000173/2024-2025 | 3171/HUG | 10/09/2024 | 06/08/2025 | OSMAN SEKH | 32.29 | 0 | 0 | 100
8 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Shifting of oh line at Udaypur w/s scheme for construction and function of pump house. As per application PHE Department Application No- 100000125219 Reference ID- 860320319 SM Code- 18308 |  |  | BILL/02806/2024-2025 | 661 | 09/01/2025 | 09/01/2025 | WBSEDCL | 1.15 | 0 | 0 | 0
9 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Quotation for New Service connection at Udaypur water supply scheme TW No IV in Khanakul-I Block SM/18308 |  |  | BILL/01017/2025-2026 |  | 05/06/2025 | 05/06/2025 | WBSEDCL | 4.48 | 0 | 0 | 0
10 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Suplimentry Quotation for Shifting of OH Line at Udaypur W/S Scheme,PH No-I for Construction of Reservoir under Electrical division,PHE Dte.(SM/18308). Application Id-100000131844, Reference Id-860327964. |  |  | BILL/03417/2024-2025 | 742 | 27/03/2025 | 27/03/2025 | WBSEDCL | 0.02 | 0 | 0 | 0
11 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 01/01/2026 | TECHVISION | 14.8 | 0 | 0 | 20
12 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED UDAYPUR PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18308 | New | Quotation for New Service connection at Udaypur ph no-4 in Khanakul-I Block SM/18308 |  |  | BILL/00559/2025-2026 |  | 07/05/2025 | 07/05/2025 | WBSEDCL | 4.69 | 0 | 0 | 0
Total | [13 empty] | 3641.22 | 258.22 | 7.09