## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-I | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Material Requisition To Resource Division |  |  | RTOR000479/2023-2024 | 3057/8/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 11.45 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-I | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for UDNA water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000814/2023-2024 | 3159/ED | 27/07/2023 | 25/10/2023 | MAA KALI ENTERPRISE | 20.23 | 14.81 | 73.2 | 100
3 | HOOGHLY | Khanakul-I | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Udna water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002471/2023-2024 | 332/ED | 21/02/2024 | 21/05/2024 | MAA KALI ENTERPRISE | 21.44 | 15.9 | 74.16 | 20
4 | HOOGHLY | Khanakul-I | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Sinking of 3 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-II and UDNA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000842/2023-2024 | 722/HUG | 05/03/2024 | 04/05/2024 | ANIRUDDHA FARUQUE | 48.17 | 26.24 | 54.47 | 100
5 | HOOGHLY | Khanakul-I | Electrical | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Quotation of New Service Connection for UDNA w/s Scheme, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18309) Application No-5004114171 Reference Id-503617472 |  |  | BILL/00233/2024-2025 | 83 | 22/04/2024 | 22/04/2024 | WBSEDCL | 3.38 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-I | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 01/04/2026 | MACKINTOSH BURN LIMITED | 3480.01 | 202.35 | 5.81 | 45
7 | HOOGHLY | Khanakul-I | Hooghly Division | Udna Piped Water Supply Scheme, Block-Khanakul I, District- Hooghly | SM/18309 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) PATUL PWSS (ii) GHOSHPUR PWSS (iii) UDNA PWSS (iv) POLE PWSS (v) GOBINDAPUR PWSS (vi) THAKURANICHAK PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000436/2024-2025 | 800/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 3585.62 | 259.3 | 7.23