## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-I | Electrical | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | SM/18310 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for POL water supply scheme, T.W. No.- I, II & III, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000813/2023-2024 | 3158/ED | 27/07/2023 | 25/10/2023 | DAS ENTERPRISE | 30.48 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-I | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | SM/18310 | New | Material Requisition To Resource Division |  |  | RTOR000495/2023-2024 | 3057/2/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.44 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-I | Electrical | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | SM/18310 | New | Quotation money deposition for new service connection at POL w/s scheme, T.W. No.-I, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004036811/Quot/03 Reference ID- 503576702 SM Code- 18310 |  |  | BILL/06218/2023-2024 | 821 | 01/03/2024 | 01/03/2024 | WBSEDCL | 3.87 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-I | Electrical | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | SM/18310 | New | Quotation money deposition for new service connection at POL w/s scheme, T.W. No.-II, Dist.-Hooghly, under Electrical Division, PHE Dte. Application No.- 5004037073/Quot/03 Reference ID- 503576717 SM Code- 18310 |  |  | BILL/06217/2023-2024 | 820 | 01/03/2024 | 01/03/2024 | WBSEDCL | 3.54 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-I | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | SM/18310 | New | MAHISGOT (ZONE-I), MAHISGOT (ZONE-II), POL, RADHABALLAVPUR (ZONE-I), UDAYPUR, UDNA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000549/2023-2024 | 3139/HUG | 16/10/2023 | 01/01/2026 | MACKINTOSH BURN LIMITED | 3480.01 | 298.46 | 8.58 | 45
6 | HOOGHLY | Khanakul-I | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | SM/18310 | New | Sinking of 2 nos 300 X200 mm dia Tube Well ,210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of POL W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000248/2024-2025 | 3527/HUG | 22/10/2024 | 31/05/2025 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 32.12 | 0 | 0 | 50
7 | HOOGHLY | Khanakul-I | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | SM/18310 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at POL (2Nos.), MOSTAFAPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000222/2024-2025 | 3434/HUG | 03/10/2024 | 28/09/2025 | DIBYENDU DHARA | 47.26 | 0 | 0 | 50
8 | HOOGHLY | Khanakul-I | Hooghly Division | Pol Piped Water Supply Scheme, Block- Khanakul-I, District-Hooghly | SM/18310 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. |  |  | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 06/04/2025 | TECHVISION | 14.8 | 0 | 0 | 0
Total | [13 empty] | 3631.53 | 298.46 | 8.22