## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | MUNDALIKA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR At ZONE-I & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000276/2023-2024 | 2295/HUG | 03/08/2023 | 30/07/2025 | GHOSH CONCERN | 585.3 | 228.02 | 38.96 | 50
2 | HOOGHLY | Jangipara | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mundalika water supply scheme, Zone-I, T.W. No. I & II and Zone-II, T.W. No. I & II Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000821/2023-2024 | 3176/ED | 28/07/2023 | 01/04/2025 | R.N.S. TRADING | 43.65 | 0 | 0 | 10
3 | HOOGHLY | Jangipara | Hooghly Division | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | MUNDALIKA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR At ZONE-I & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000278/2023-2024 | 2293/HUG | 03/08/2023 | 15/04/2026 | JAL PRAVAHIKA PVT. LTD | 608.12 | 201.6 | 33.15 | 20
4 | HOOGHLY | Jangipara | Hooghly Division | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | Material Requisition To Resource Division |  |  | RTOR000514/2023-2024 | 3060/10/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 27.04 | 0 | 0 | 0
5 | HOOGHLY | Jangipara | Hooghly Division | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | Material Requisition To Resource Division |  |  | RTOR000333/2023-2024 | 3005/1/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 65.04 | 0 | 0 | 0
6 | HOOGHLY | Jangipara | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | Quotation Bill for New Service Connection at Mundalika W/S. Sch. PH-I, Z-II |  |  | BILL/04647/2023-2024 | 623 | 08/01/2024 | 08/01/2024 | WBSEDCL | 8.9 | 0 | 0 | 0
7 | HOOGHLY | Jangipara | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | Quotation for New service connection at Mundalika W/S. Sch.Z-I, PH-I |  |  | BILL/06222/2023-2024 | 826 | 01/03/2024 | 01/03/2024 | WBSEDCL | 5.4 | 0 | 0 | 0
8 | HOOGHLY | Jangipara | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | Quotation Bill for New Service Connection at Mundalika W/S. Sch. PH-II, Z-II |  |  | BILL/04645/2023-2024 | 622 | 08/01/2024 | 08/01/2024 | WBSEDCL | 12.14 | 0 | 0 | 0
9 | HOOGHLY | Jangipara | Electrical | MUNDALIKA PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY | SM/18320 | New | Quotation Bill for New Service Connection at Mundalika W/S. Sch. Z-I, PH-I |  |  | BILL/04688/2023-2024 | 664 | 11/01/2024 | 11/01/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
Total | [13 empty] | 1358.96 | 429.61 | 31.61