## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2022-2023 | 79/22/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 38.01 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-II, Z-II, |  |  | BILL/04318/2023-2024 | 425 | 17/11/2023 | 17/11/2023 | WBSEDCL | 3.94 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Quotation Bill for for New Service Connection at Krishnanagar W/S. Sch. PH-I, Z-II |  |  | BILL/04317/2023-2024 | 426 | 17/11/2023 | 17/11/2023 | WBSEDCL | 5.3 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000257/2024-2025 | 3530/HUG | 22/10/2024 | 06/12/2024 | PADMA ENGINEERING CO. | 47.5 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000407/2024-2025 | 3783/HUG | 25/11/2024 | 24/01/2025 | DAS CONSTRUCTION | 55.5 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNANAGAR Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000324/2024-2025 | 3665/HUG | 13/11/2024 | 11/02/2025 | M/S B N ENTERPRISE | 16.12 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000190/2024-2025 | 1205/ED | 14/06/2024 | 12/09/2024 | SWAPAN ENTERPRISE | 10.75 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of NATIBPUR , SAIDPUR Zone-II , KRISHNANAGAR Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000171/2024-2025 | 3170/HUG | 10/09/2024 | 25/10/2024 | BIMAL KUMAR HALDER | 48.47 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KRISHNANAGAR PIPED W/S SCHEME, T.W. No. V, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000193/2024-2025 | 1207/ED | 14/06/2024 | 12/09/2024 | D.S. ENTERPRISE | 10.74 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte |  |  | ORD/000405/2024-2025 | 3782/HUG | 25/11/2024 | 24/01/2025 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of KRISHNANAGAR Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte |  |  | ORD/000300/2024-2025 | 3660/HUG | 13/11/2024 | 11/02/2025 | SUDIPTA DAS | 16.08 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Krishnanagar water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000992/2023-2024 | 3788/ED | 26/09/2023 | 25/12/2023 | GLACIER ENGINEERING CO. | 21.75 | 0 | 0 | 40
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Augmentation of KRISHNANAGAR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls in ZONE-II & Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, LDS, FHTC in ZONE-I under KHANAKUL-I Block, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000224/2023-2024 | 2036/HUG | 13/07/2023 | 02/10/2025 | M/S PRADYUT KUMAR HAZRA | 642.46 | 0 | 0 | 15
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF KRISHNANAGAR PIPED W/S SCHEME UNDER KHANAKUL-I BLOCK | SM/18339 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS - 6 nos (2) KRISHNANAGAR PWSS - 4nos (3) PATUL PWSS - 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002646/2024-2025 | 810/Arg | 23/08/2024 | 22/09/2024 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
Total | [13 empty] | 972.73 | 0 | 0