## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Hooghly Division | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | SM/18345 | New | Material Requisition To Resource Division |  |  | RTOR000410/2023-2024 | 3057/47/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.24 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Hooghly Division | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | SM/18345 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HAYATPUR and ARUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000843/2023-2024 | 723/HUG | 05/03/2024 | 04/05/2024 | SPG ENTERPRISES | 64.34 | 0 | 0 | 50
3 | HOOGHLY | Khanakul-II | Electrical | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | SM/18345 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HAYATPUR PIPED W/S SCHEME, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000154/2024-2025 | 1177/ED | 14/06/2024 | 12/09/2024 | M/S G P ENTERPRISE | 10.74 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Electrical | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | SM/18345 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HAYATPUR PIPED W/S SCHEME, T.W. No. IV, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000155/2024-2025 | 1178/ED | 14/06/2024 | 12/09/2024 | M/S. UTTAM KUMAR CHATTERJEE. | 10.74 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Electrical | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | SM/18345 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hayatpur water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000816/2023-2024 | 3161/ED | 27/07/2023 | 01/04/2025 | GLACIER ENGINEERING CO. | 21.83 | 0 | 0 | 50
6 | HOOGHLY | Khanakul-II | Hooghly Division | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | SM/18345 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 01/01/2026 | MACKINTOSH BURN LIMITED | 5743.06 | 0 | 0 | 50
7 | HOOGHLY | Khanakul-II | Hooghly Division | Hayatpur Piped Water Supply Scheme, Block-Khanakul-II, District-Hooghly. | SM/18345 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 06/04/2025 | TECHVISION | 14.8 | 0 | 0 | 0
Total | [13 empty] | 5884.75 | 0 | 0