## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | SM/18346 | New | PASCHIM NARAYANPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under HARIPAL Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Tarakeswar Block Junior Engineer | ORD/000315/2023-2024 | 2387/HUG | 09/08/2023 | 29/10/2025 | PRASUN ENTERPRISE (PRASUN BISWAS) | 714.76 | 164.13 | 22.96 | 10
2 | HOOGHLY | Haripal | Electrical | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | SM/18346 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Paschim Narayanpur water supply scheme, T.W. No.- I & II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000819/2023-2024 | 3175/ED | 28/07/2023 | 01/07/2025 | M/S A.K BANERJEE | 20.35 | 15.04 | 73.89 | 30
3 | HOOGHLY | Haripal | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | SM/18346 | New | Material Requisition To Resource Division |  |  | RTOR000195/2022-2023 | 109/ 10/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 73.57 | 0 | 0 | 0
4 | HOOGHLY | Haripal | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | SM/18346 | New | Material Requisition To Resource Division |  |  | RTOR000404/2023-2024 | 3058/5/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 16.53 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Electrical | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | SM/18346 | New | Quotation Bill for New Service Connection at Paschim Narayanpur W/S. Sch.TW-I |  |  | BILL/04582/2023-2024 | 587 | 28/12/2023 | 28/12/2023 | WBSEDCL | 3.95 | 0 | 0 | 0
6 | HOOGHLY | Haripal | Electrical | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | SM/18346 | New | Quotation Bill for New Service Connection at Paschim Narayanpur W/S. Sch.TW-II |  |  | BILL/04581/2023-2024 | 586 | 28/12/2023 | 28/12/2023 | WBSEDCL | 3.91 | 0 | 0 | 0
7 | HOOGHLY | Haripal | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | SM/18346 | New | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Kamarkundu (Zone-4) 1st T/W site & Paschim Narayanpur 1st T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000290/2024-2025 | 927/Chan | 05/11/2024 | 20/11/2024 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
8 | HOOGHLY | Haripal | Hooghly Division | GROUND WATER BASED WATER SUPPLY SCHEME FOR PASCHIM NARAYANPUR PWSS, UNDER HOOGHLY DIVISION , BLOCK : HARIPAL, DISTRICT : HOOGHLY | SM/18346 | New | ROAD RESTORATION PAYMENT TO PWD FOR HAZRA MORE TO SUNDARPUR MORE ROAD |  |  | BILL/00664/2024-2025 | BP-2024-25-498 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER, (PWD) HOOGHLY CONSTRUCTION DIVISION | 37.84 | 0 | 0 | 0
Total | [13 empty] | 871.87 | 179.16 | 20.55