## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHYAMPUR PIPED W/S SCHEME, T.W. No. V, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000165/2024-2025 | 1187/ED | 14/06/2024 | 12/09/2024 | COOLING CARE CENTER | 10.74 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of SHYAMPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000377/2024-2025 | 3719/HUG | 19/11/2024 | 18/01/2025 | SIBSANKAR CHOWDHURY | 51.74 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Electric quot. of WBSEDCL for New Connection of Shyampur T/W-IV W/S scheme under ED PHE Dte (SM/18347) |  |  | BILL/01356/2024-2025 | 338 | 30/07/2024 | 30/07/2024 | WBSEDCL | 4.57 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Shyampur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18347) |  |  | BILL/01613/2024-2025 | 372 | 12/08/2024 | 12/08/2024 | WBSEDCL | 26.41 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Augmentation of SHYAMPUR Piped Water Supply Scheme with Sinking of 3 Nos. tube-well within ZONE-I, II & III, Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, LDS, FHTC in ZONE-I, LDS, FHTC, construction of switch-rooms & boundary walls in ZONE-II, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & LDS, RISING MAIN, FHTC, construction of switch-rooms & boundary walls in ZONE-III under PURSURAH Block, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000275/2023-2024 | 2292/HUG | 03/08/2023 | 03/11/2025 | SIBSANKAR CHOWDHURY | 745.98 | 0 | 0 | 45
6 | HOOGHLY |  | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyampur water supply scheme, T.W. No.- I, II, III & IV, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000820/2023-2024 | 3174/ED | 28/07/2023 | 02/05/2025 | H.K.DAS & CO. | 43.01 | 0 | 0 | 25
7 | HOOGHLY |  | Hooghly Division | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) BAIKUNTHAPUR PWSS (ii) BHANGAMORA PWSS (iii) CHILADANGI PWSS (iv) SAOTA PWSS (v) SHYAMPUR PWSS (vi) MAHISGHOT-(ZONE-I) PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000440/2024-2025 | 801/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 883.4 | 0 | 0