## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHYAMPUR PIPED W/S SCHEME, T.W. No. V, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000165/2024-2025 | 1187/ED | 14/06/2024 | 12/09/2024 | COOLING CARE CENTER | 10.74 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of SHYAMPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000377/2024-2025 | 3719/HUG | 19/11/2024 | 18/01/2025 | SIBSANKAR CHOWDHURY | 51.74 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Electric quot. of WBSEDCL for New Connection of Shyampur T/W-IV W/S scheme under ED PHE Dte (SM/18347) |  |  | BILL/01356/2024-2025 | 338 | 30/07/2024 | 30/07/2024 | WBSEDCL | 4.57 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Shyampur T/W-III W/S scheme under Electrical Division PHE Dte. (SM/18347) |  |  | BILL/01613/2024-2025 | 372 | 12/08/2024 | 12/08/2024 | WBSEDCL | 26.41 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Augmentation of SHYAMPUR Piped Water Supply Scheme with Sinking of 3 Nos. tube-well within ZONE-I, II & III, Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, LDS, FHTC in ZONE-I, LDS, FHTC, construction of switch-rooms & boundary walls in ZONE-II, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & LDS, RISING MAIN, FHTC, construction of switch-rooms & boundary walls in ZONE-III under PURSURAH Block, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000275/2023-2024 | 2292/HUG | 03/08/2023 | 03/11/2025 | SIBSANKAR CHOWDHURY | 745.98 | 247.41 | 33.17 | 45
6 | HOOGHLY |  | Electrical | Augmentation of Shyampur Piped Water Supply Scheme, Block- Pursura, District-Hooghly. | SM/18347 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyampur water supply scheme, T.W. No.- I, II, III & IV, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000820/2023-2024 | 3174/ED | 28/07/2023 | 02/05/2025 | H.K.DAS & CO. | 43.01 | 2.77 | 6.44 | 25
Total | [13 empty] | 882.44 | 250.18 | 28.35