## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Material Requisition To Resource Division |  |  | RTOR000376/2023-2024 | 3002/5/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 54.23 | 0 | 0 | 0
2 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Z-II, TW-II |  |  | BILL/03827/2023-2024 | 285 | 18/09/2023 | 18/09/2023 | WBSEDCL | 3.29 | 0 | 0 | 0
3 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Electric quot for Ghol Digrui Zone-II T/W-I W/S scheme |  |  | BILL/02719/2023-2024 | 166 | 04/08/2023 | 04/08/2023 | WBSEDCL | 3.16 | 0 | 0 | 0
4 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/002468/2023-2024 | 329/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
5 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000815/2023-2024 | 3160/ED | 27/07/2023 | 25/10/2023 | DIPALI CONSTRUCTION | 21.49 | 0 | 0 | 30
6 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | GHOL DIGRUI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000223/2023-2024 | 2035/HUG | 12/07/2023 | 07/04/2024 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 568.38 | 0 | 0 | 60
7 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | GHOL DIGRUI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000227/2023-2024 | 2035/hug | 13/07/2023 | 28/03/2025 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 568.38 | 0 | 0 | 80
Total | [13 empty] | 1229.36 | 0 | 0