## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Material Requisition To Resource Division |  |  | RTOR000376/2023-2024 | 3002/5/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 54.23 | 0 | 0 | 0
2 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Quotation Bill for New Service Connection at Ghol Digrui W/S. Sch. Z-II, TW-II |  |  | BILL/03827/2023-2024 | 285 | 18/09/2023 | 18/09/2023 | WBSEDCL | 3.29 | 0 | 0 | 0
3 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Electric quot for Ghol Digrui Zone-II T/W-I W/S scheme |  |  | BILL/02719/2023-2024 | 166 | 04/08/2023 | 04/08/2023 | WBSEDCL | 3.16 | 0 | 0 | 0
4 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No.- I & II, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000815/2023-2024 | 3160/ED | 27/07/2023 | 25/10/2023 | DIPALI CONSTRUCTION | 21.49 | 21.46 | 99.86 | 30
5 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | GHOL DIGRUI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000223/2023-2024 | 2035/HUG | 12/07/2023 | 07/04/2024 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 568.38 | 36.04 | 6.34 | 60
6 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | GHOL DIGRUI (ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000227/2023-2024 | 2035/hug | 13/07/2023 | 28/03/2025 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 568.38 | 418.05 | 73.55 | 80
7 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GHOLDGRUI PWSS(Z-II)- 3no¿s, (2) KELEPARA PWSS- 2 no¿s, (3) RASULPUR PWSS- 5 no¿s, (4) BHANGAMORA PWSS- 1 no¿s, (5) SHYAMPUR PWSS(Z-III)- 2 no¿s, (6) GOPALDAHA PWSS- 1 no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002302/2024-2025 | 1156/Arg | 10/12/2024 | 10/01/2025 | KARALI MOHAN KHAMRUI | 0.98 | 0 | 0 | 99
8 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Service connection charges for Gholdiguri water supply scheme ZONE -II,TW NO-V. |  |  | BILL/01105/2025-2026 | 42151 | 30/07/2025 | 30/07/2025 | WBSEDCL | 3.99 | 0 | 0 | 0
9 | HOOGHLY | Pursura | Hooghly Division | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for GHOLDIGRUI ZONE-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000286/2024-2025 | 3668/HUG | 13/11/2024 | 01/02/2026 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 52.78 | 0 | 0 | 70
10 | HOOGHLY | Pursura | Electrical | Ghol Digrui (Zone-II) Piped Water Supply Scheme , Block- Pursura, District-Hooghly | SM/18348 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghol Digrui water supply scheme, Zone-II, T.W. No. III, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1,Junior Engineer3 | ORD/002468/2023-2024 | 329/ED | 21/02/2024 | 01/06/2026 | DEY ENTERPRISE | 10.43 | 0 | 0 | 5
Total | [13 empty] | 1287.11 | 475.55 | 36.95