## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-I | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | Material Requisition To Resource Division |  |  | RTOR000503/2023-2024 | 3060/6/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 26.05 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-I | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Bhagabatipur-I PWSS 2. Bhagabatipur-II PWSS 3. Jagmohanpur PWSS 4. Bandhpur PWSS 5. Haripur PWSS 6. Pairagacha PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000940/2023-2024 | 110/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.95 | 100 | 80
3 | HOOGHLY | Chanditala-I | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT BHAGABATIPUR Zone-I HW SITE AND 2ND TW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000135/2024-2025 | 424/SER | 31/07/2024 | 15/08/2024 | SUNITI MAIRA | 0.68 | 0.66 | 97.1 | 95
4 | HOOGHLY | Chanditala-I | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-I, P.H. No.-II, Hooghly. Application No. 5004066730 Ref ID: 503597305 |  |  | BILL/00236/2024-2025 | 87 | 23/04/2024 | 23/04/2024 | WBSEDCL | 4.55 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-I | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | PAYMENT TO ROAD RESTORATION TO PWD KALACHARA BHAGABATIPUR ROAD |  |  | BILL/00684/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 96.95 | 0 | 0 | 0
6 | HOOGHLY | Chanditala-I | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-II, P.H. No.-II, Hooghly. Application No. 5004042700 Ref ID: 503581618 |  |  | BILL/00119/2024-2025 | 44 | 09/04/2024 | 09/04/2024 | WBSEDCL | 10.61 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-I | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | Quotation for new service connection of Bhogatipur W/S. Sch. PH-I |  |  | BILL/06052/2023-2024 | 739 | 08/02/2024 | 08/02/2024 | WBSEDCL | 6.31 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-I | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | Quotation bill for new service connection charges at Bhagabatipur PWSS Zone-II, P.H. No.-I, Hooghly. Application No. 5004034017 Ref ID: 503576013 |  |  | BILL/00237/2024-2025 | 86 | 23/04/2024 | 23/04/2024 | WBSEDCL | 5.36 | 0 | 0 | 0
9 | HOOGHLY | Chanditala-I | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | BHAGABATIPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-I Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000280/2023-2024 | 2320/HUG | 04/08/2023 | 27/05/2025 | S GHOSH AND ASSOCIATES PVT LTD. | 570.37 | 42.94 | 7.53 | 20
10 | HOOGHLY | Chanditala-I | Hooghly Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | BHAGABATIPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under CHANDITALA-I Block of Serampore Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001026/2023-2024 | 2021/HUG | 11/07/2023 | 04/04/2025 | TIRUPATI ENTERPRISES | 498.14 | 305.03 | 61.23 | 30
11 | HOOGHLY | Chanditala-I | Electrical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I, DISTRICT : HOOGHLY. | SM/18373 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Bhagabatipur water supply scheme, Zone - I, T.W. No. I & II and Zone - II, T.W. No. I & II, Block: Chanditala-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000940/2023-2024 | 3619/ED | 29/08/2023 | 05/04/2028 | M/S BIPUL BANERJEE | 46.53 | 33.79 | 72.62 | 60
Total | [13 empty] | 1266.51 | 383.38 | 30.27