## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Construction of 600 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & FHTC In Daluigaccha Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-VI) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000396/2023-2024 | 2609/HUG | 29/08/2023 | 25/05/2024 | SUJATA CONSTRUCTION | 227.52 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-I |  |  | BILL/04571/2023-2024 | 575 | 27/12/2023 | 27/12/2023 | WBSEDCL | 4.52 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-VI, TW-III |  |  | BILL/04570/2023-2024 | 576 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.64 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation for new service connection charge at Kamarkundu PWSS, Zone-VI, TW - II |  |  | BILL/04586/2023-2024 | 589 | 28/12/2023 | 28/12/2023 | WBSEDCL | 3.79 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-IV) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000574/2023-2024 | 3113/HUG | 13/10/2023 | 06/06/2025 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 204.08 | 0 | 0 | 50
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Balance FHTC in SINGUR CT (P) Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) |  | ORD/000879/2023-2024 | 763/HUG | 05/03/2024 | 20/03/2024 | SRI KRISHNA ENTERPRISE | 7.1 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of KAMARKUNDU PWSS under ChandannagarSub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000481/2024-2025 | 4057/HUG | 19/12/2024 | 18/04/2025 | SWASTIK ENTERPRISE | 13 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Balance FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000871/2023-2024 | 752/HUG | 05/03/2024 | 20/03/2024 | ARUN SEAL AND CO. | 9.77 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Laying left out pipe line For Augmentation of KAMARKUNDU Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000873/2023-2024 | 761/HUG | 05/03/2024 | 20/03/2024 | BOSE ENTERPRISE (RATUL BOSE) | 7.28 | 0 | 0 | 100
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Laying additional pipe line For Restoration of water supply Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000874/2023-2024 | 760/HUG | 05/03/2024 | 20/03/2024 | BOSE ENTERPRISE (RATUL BOSE) | 9.97 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Laying additional pipe line & FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000875/2023-2024 | 754/HUG | 05/03/2024 | 20/03/2024 | ARUN SEAL AND CO. | 9.79 | 0 | 0 | 100
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Laying additional pipe line & FHTC in SINGUR (CT ) & BURIGEON Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000867/2023-2024 | 757/HUG | 05/03/2024 | 20/03/2024 | DAS ENTERPRISE (SAMIR DAS) | 9.97 | 0 | 0 | 100
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Making of 2 nos 1.8m x 1.45m x 2.1m KIOSK at Kamarkundu (Z-7) 1st T/W site & Kamarkundu (Z-7) 2nd T/W site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000281/2024-2025 | 920/Chan | 05/11/2024 | 20/11/2024 | AMBIAN INFRASTRUCTURE | 0.97 | 0 | 0 | 100
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Laying additional pipe line For Restoration of water supply Of KAMARKUNDU Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000870/2023-2024 | 759/HUG | 05/03/2024 | 20/03/2024 | ARUN SEAL AND CO. | 9.98 | 0 | 0 | 100
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Balance FHTC in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000877/2023-2024 | 762/HUG | 05/03/2024 | 20/03/2024 | DAS ENTERPRISE (SAMIR DAS) | 9.8 | 0 | 0 | 100
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Laying additional pipe line in various Mouzas For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000872/2023-2024 | 753/HUG | 05/03/2024 | 20/03/2024 | ARUN SEAL AND CO. | 9.78 | 0 | 0 | 100
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Laying additional pipe line & FHTC in BURIGAON Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000876/2023-2024 | 755/HUG | 05/03/2024 | 20/03/2024 | ARUN SEAL AND CO. | 10 | 0 | 0 | 100
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Laying additional pipe line & FHTC in SINGUR(CT)Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-II) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000878/2023-2024 | 756/HUG | 05/03/2024 | 20/03/2024 | DAS ENTERPRISE (SAMIR DAS) | 9.97 | 0 | 0 | 100
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Gopalnagar W/S. Sch.TW-II |  |  | BILL/04585/2023-2024 | 596A | 29/12/2023 | 29/12/2023 | WBSEDCL | 3.79 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-III |  |  | BILL/05911/2023-2024 | 719 | 29/01/2024 | 29/01/2024 | WBSEDCL | 3.47 | 0 | 0 | 0
21 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-I, Z-VII |  |  | BILL/06107/2023-2024 | 773 | 19/02/2024 | 19/02/2024 | WBSEDCL | 4.67 | 0 | 0 | 0
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation money deposition for new service connection at Kamarkundu w/s scheme, Zone- VI, T.W. No.-IV, Dist.-Hooghly under PHE Dte. Application No- 5004229746 Reference ID- 503663995 SM Code- 18397 |  |  | BILL/00822/2024-2025 | 218 | 18/06/2024 | 18/06/2024 | WBSEDCL | 4.94 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | PAYMENT FOR ROAD RESTORATION |  |  | BILL/00268/2024-2025 | BP-2024-25-185 | 06/06/2024 | 06/06/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 26.97 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Restoration Works for Singur-Ugly Road |  |  | BILL/01133/2023-2024 | BP-2023-24-852 | 21/02/2024 | 21/02/2024 | EXECUTIVE ENGINEER, HOOGHLY DIVISION PWD | 1.49 | 0 | 0 | 0
25 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-II |  |  | BILL/04854/2023-2024 | 673 | 17/01/2024 | 17/01/2024 | WBSEDCL | 6.51 | 0 | 0 | 0
26 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch. Z-II, TW-III |  |  | BILL/05985/2023-2024 | 730 | 05/02/2024 | 05/02/2024 | CESC LIMITED. | 5.17 | 0 | 0 | 0
27 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-VI |  |  | BILL/05915/2023-2024 | 717 | 29/01/2024 | 29/01/2024 | WBSEDCL | 4.81 | 0 | 0 | 0
28 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation for new service connection at Kamarkundu W/S Sch., Zone - V, T/W No. - I,[SM/18397], under Singur CCC, WBSEDCL, Ref. Id. - 503706067, Dt. - 30-07-2024, Application No. - 5004320836 |  |  | BILL/01591/2024-2025 | 356 | 07/08/2024 | 07/08/2024 | WBSEDCL | 7.25 | 0 | 0 | 0
29 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-II, Z-IV |  |  | BILL/06108/2023-2024 | 772 | 19/02/2024 | 19/02/2024 | WBSEDCL | 7.2 | 0 | 0 | 0
30 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | PAYMENT FOR ROAD RESTORATION |  |  | BILL/00267/2024-2025 | BP-2024-25-184 | 06/06/2024 | 06/06/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 14.63 | 0 | 0 | 0
31 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-I |  |  | BILL/05913/2023-2024 | 718 | 29/01/2024 | 29/01/2024 | WBSEDCL | 3.02 | 0 | 0 | 0
32 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation for new service connnection at Kamarkundu W/S. Sch. TW-II, Z-VII |  |  | BILL/06106/2023-2024 | 771 | 19/02/2024 | 19/02/2024 | WBSEDCL | 4.87 | 0 | 0 | 0
33 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | PAYMENT FOR ROAD RESTORATION |  |  | BILL/00266/2024-2025 | BP-2024-25-183 | 06/06/2024 | 06/06/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 23.44 | 0 | 0 | 0
34 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-I |  |  | BILL/05906/2023-2024 | 720 | 31/01/2024 | 31/01/2024 | WBSEDCL | 4.85 | 0 | 0 | 0
35 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Quotation Bill for New Service Connection at Kamarkundu W/S. Sch.Z-IV |  |  | BILL/05910/2023-2024 | 716 | 29/01/2024 | 29/01/2024 | WBSEDCL | 4.87 | 0 | 0 | 0
36 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-III) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000248/2023-2024 | 2111/HUG | 20/07/2023 | 02/08/2025 | S.K. GHOSH | 289.99 | 0 | 0 | 10
37 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-VII) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000249/2023-2024 | 2112/HUG | 20/07/2023 | 01/01/2026 | S. HATI | 288.45 | 0 | 0 | 70
38 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-I) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000246/2023-2024 | 2109/HUG | 20/07/2023 | 02/09/2025 | BAPPADITYA BANERJEE | 318.37 | 0 | 0 | 33
39 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | AUGMENTATION of KAMARKUNDU (ZONE-V) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of CHANDANNAGAR Sub Division, District:- Hooghly [AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000573/2023-2024 | 3114/HUG | 13/10/2023 | 06/04/2025 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 129.13 | 0 | 0 | 50
40 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Hiring of Additional Diesel Motor Car (Non AC) for inspecting of JJM Schemes on daily hire rate basis for 05 months having contract carriage permit for plying within West Bengal from Regional Transport Authority for the office of the Asst Engineer Chandannagar Sub-Division, PHE Dte.[ Period from 01.12.2023 to 30.04.2024]. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000657/2023-2024 | 930/Chan | 30/11/2023 | 30/04/2024 | PAUL AUTOMOBILES | 0.72 | 0 | 0 | 0
41 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kamarkundu water supply scheme at different zone, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001864/2023-2024 | 50/ED | 05/01/2024 | 05/01/2026 | DAS ENTERPRISE | 172.16 | 0 | 0 | 55
42 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | 1st Continuation order for the work of Hiring of Additional Diesel Motor Car (Non AC) for inspecting of JJM Schemes on daily hire rate basis for 02 months having contract carriage permit for plying within West Bengal from Regional Transport Authority for the office of the Asst Engineer Chandannagar Sub-Division, PHE Dte. (Period from 01/05/2024 to 30/06/2024) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000023/2024-2025 | 476/Chan | 26/04/2024 | 26/06/2024 | PAUL AUTOMOBILES | 0.29 | 0 | 0 | 0
43 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Construction of structural shed for storing Mechanical pumps and machineries at Kamarkundu Zone-II OHR work site under Chandannagar Sub division within Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000247/2025-2026 | 897/CHAN | 21/07/2025 | 05/08/2025 | TOTON MONDAL | 4.88 | 0 | 0 | 0
44 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Repairing & Renovation work of Existing additional Room at under Kamarkundu zone-3 water supply scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000298/2025-2026 | 931/CHAN | 21/07/2025 | 10/08/2025 | ASHA ENTERPRISE | 4.98 | 0 | 0 | 50
45 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Construction of switch-rooms & boundary wall at different TW site , LDS & FHTC in Gopalnagar Mouza For AUGMENTATION Of KAMARKUNDU (ZONE-VI) Piped Water Supply Scheme under Chandannagar Sub Division Block-SINGUR , District:- Hooghly[AUGMENTATION ] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000266/2023-2024 | 2240/HUG | 01/08/2023 | 21/07/2025 | MONDAL PRECISION PRIVATE LIMITED | 425.43 | 0 | 0 | 25
46 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMARKUNDU MIRZAPUR BAKIPUR | SM/18397 | Augmentation | Repair, renovation work & construction of new toilet with other allied works at the Head Work site of Kamarkundu PWSS under Chandannagar Sub Division Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000969/2023-2024 | 288/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.9 | 0 | 0 | 100
Total | [13 empty] | 2328.18 | 0 | 0