## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Material Requisition To Resource Division |  |  | RTOR000400/2023-2024 | 3057/51/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.68 | 0 | 0 | 0
2 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RASULPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000289/2024-2025 | 3654/HUG | 13/11/2024 | 11/02/2025 | BAKSHI ENTERPRISE | 16.15 | 0 | 0 | 0
3 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000162/2024-2025 | 1185/ED | 14/06/2024 | 12/09/2024 | M/S, GHOSH ENTERPRISE | 10.73 | 0 | 0 | 0
4 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of NATIBPUR KRISHNANAGAR Zone-I , RASULPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte |  |  | ORD/000405/2024-2025 | 3782/HUG | 25/11/2024 | 24/01/2025 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 55.13 | 0 | 0 | 0
5 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RASULPUR PIPED W/S SCHEME, T.W. No. III, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000161/2024-2025 | 1184/ED | 14/06/2024 | 12/09/2024 | RISHAV ENTERPRISE | 10.75 | 0 | 0 | 0
6 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of RASULPUR, SHYAMBALLAVPUR , DIHIBAGNAN W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000264/2024-2025 | 3531/HUG | 22/10/2024 | 06/12/2024 | PADMA ENGINEERING CO. | 47.49 | 0 | 0 | 0
7 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | RASULPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under PURSURAH Block of Arambag Sub-Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Pursurah Block Junior Engineer | ORD/000256/2023-2024 | 2188/HUG | 26/07/2023 | 29/09/2025 | KHAN ENTERPRISE | 741.7 | 0 | 0 | 5
8 | HOOGHLY | Pursura | Electrical | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Soaluk water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/002473/2023-2024 | 334/ED | 21/02/2024 | 01/05/2025 | DEY ENTERPRISE | 10.43 | 0 | 0 | 35
9 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Sinking of 2 Nos. Additional tube-well at Rasulpur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/002250/2024-2025 | 651/HUG | 10/03/2025 | 09/04/2025 | AUXILIARY TUBEWELL DRILLERS | 29.39 | 0 | 0 | 0
10 | HOOGHLY | Pursura | Hooghly Division | GROUND WATER BASED RASULPUR PIPED WATER SUPPLY SCHEME IN PURSURA BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18429 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GHOLDGRUI PWSS(Z-II)- 3no¿s, (2) KELEPARA PWSS- 2 no¿s, (3) RASULPUR PWSS- 5 no¿s, (4) BHANGAMORA PWSS- 1 no¿s, (5) SHYAMPUR PWSS(Z-III)- 2 no¿s, (6) GOPALDAHA PWSS- 1 no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002302/2024-2025 | 1156/Arg | 10/12/2024 | 10/01/2025 | KARALI MOHAN KHAMRUI | 0.98 | 0 | 0 | 99
Total | [13 empty] | 942.42 | 0 | 0