## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Material Requisition To Resource Division |  |  | RTOR000482/2023-2024 | 3057/6/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 12.85 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SHANTIPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000141/2024-2025 | 1167/ED | 14/06/2024 | 12/09/2024 | SRI KRISHNA NIRMAN | 10.54 | 0 | 0 | 30
3 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Quotation of New Service Connection for Shantipur w/s Scheme, Zone-I,PH No-III Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18592) Application No-5004190445 Reference Id-503647425. |  |  | BILL/00481/2024-2025 | 151 | 22/05/2024 | 22/05/2024 | WBSEDCL | 3.15 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Quotation of New service Connection at Shantipur w/s Scheme,Zone-I,PH No-I Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/18592) Application No-5004135566 Reference Id-503626938. |  |  | BILL/00329/2024-2025 | 103 | 06/05/2024 | 06/05/2024 | WBSEDCL | 10.73 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Quotation of New service Connection at Shantipur w/s Scheme,Zone-I,PH No-II Block-Goghat-II District-Hooghly under Electrical division,PHE Dte.(SM/18592) Application No-5004136337 Reference Id-503627274. |  |  | BILL/00328/2024-2025 | 102 | 06/05/2024 | 06/05/2024 | WBSEDCL | 10.8 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Shantipur water supply scheme, Zone-I, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000916/2023-2024 | 3587/ED | 28/08/2023 | 31/05/2025 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 22.26 | 0 | 0 | 30
7 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 01/07/2025 | M/S PRITI ENTERPRISE | 4251.5 | 0 | 0 | 30
8 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000847/2023-2024 | 725/HUG | 05/03/2024 | 01/01/2026 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 0 | 0 | 70
9 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002741/2024-2025 | 1149/Arg | 10/12/2024 | 10/01/2025 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
10 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PURBA RAYPUR PWSS-2nos (2) HARADITYA PWSS-4nos (3) PALASPAI PWSS- 2nos (4) JAGATPUR PWSS- 4nos (5) BARADANGAL (Z-I)-2 nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000531/2024-2025 | 812/Arg | 23/08/2024 | 22/09/2024 | M/S KHAMRUI CONSTRUCTION | 0.98 | 0 | 0 | 100
11 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED SHANTIPUR (ZONE-1) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18592 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. 1. HARISCHAK(Z-I)PWSS- 1 nos 2. HARISCHAK(Z-II)PWSS- 1nos 3. MAINAN PWSS - 2nos 4. PURBA THAKURANICHAK(Z-I)PWSS - 2nos 5. PURBA THAKURANICHAK(Z-II)PWSS- 2nos 6. GOURHATI PWSS - 2nos 7. KANPUR PWSS- 2nos 8. TANTISAL PWSS - 2nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000533/2024-2025 | 820/Arg | 23/08/2024 | 22/09/2024 | M/S KHAMRUI CONSTRUCTION | 0.98 | 0 | 0 | 100
Total | [13 empty] | 4389.08 | 0 | 0