## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-I | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Material Requisition To Resource Division |  |  | RTOR000211/2022-2023 | 127/29/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 18.93 | 0 | 0 | 0
2 | HOOGHLY | Goghat-I | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Material Requisition To Resource Division |  |  | RTOR000439/2023-2024 | 3057/30/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.98 | 0 | 0 | 0
3 | HOOGHLY | Goghat-I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sunia water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000917/2023-2024 | 3588/ED | 28/08/2023 | 26/11/2023 | A.G. ENTERPRISE | 21.49 | 10.28 | 47.81 | 15
4 | HOOGHLY | Goghat-I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Quotation of New Service Connection for Sunia w/s Scheme,PH No-IV,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18593) Application No-5004475105 Reference Id-503799038 |  |  | BILL/02473/2024-2025 | 616 | 05/12/2024 | 05/12/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
5 | HOOGHLY | Goghat-I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Quotation Bill for New Service Connection at Sunia PWSS W/S. Sch. |  |  | BILL/05994/2023-2024 | 747 | 08/02/2024 | 08/02/2024 | WBSEDCL | 4.51 | 0 | 0 | 0
6 | HOOGHLY | Goghat-I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Quotation of New Service Connection for Sunia w/S Scheme,PH No-II, Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/18593) Application No-5004479490 Reference Id-503802380 |  |  | BILL/02308/2024-2025 | 607 | 05/12/2024 | 05/12/2024 | WBSEDCL | 7.79 | 0 | 0 | 0
7 | HOOGHLY | Goghat-I | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PUKHURIA PWSS- 3 nos (2) SELAMPUR PWSS (Z-I)- 2 nos (3) SHANTIPUR PWSS (Z-I)- 1 nos (4) KOTA PWSS - 4nos (5) SUNIA PWSS - 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002741/2024-2025 | 1149/Arg | 10/12/2024 | 10/01/2025 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
8 | HOOGHLY | Goghat-I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sunia water supply scheme, T.W. No. III & IV, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000885/2023-2024 | 3458/ED | 11/08/2023 | 01/05/2025 | DIPALI CONSTRUCTION | 21.49 | 15.92 | 74.08 | 20
Total | [13 empty] | 93.52 | 26.19 | 28.01