## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat - I | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Material Requisition To Resource Division |  |  | RTOR000211/2022-2023 | 127/29/Hug | 13/01/2023 |  | Resource Division | 18.93 | 0 | 0 | 0
2 | HOOGHLY | Goghat - I | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Material Requisition To Resource Division |  |  | RTOR000439/2023-2024 | 3057/30/Hug | 11/10/2023 |  | Resource Division | 14.98 | 0 | 0 | 0
3 | HOOGHLY | Goghat - I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Quotation Bill for New Service Connection at Sunia PWSS W/S. Sch. |  |  | BILL/05994/2023-2024 | 747 | 08/02/2024 |  | WBSEDCL | 4.51 | 0 | 0 | 0
4 | HOOGHLY | Goghat - I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Quotation Bill for New Service Connection at Sunia PWSS W/S. Sch. |  |  | BILL/05994/2023-2024 | 747 | 08/02/2024 |  | WBSEDCL | 4.51 | 0 | 0 | 0
5 | HOOGHLY | Goghat - I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sunia water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000917/2023-2024 | 3588/ED | 28/08/2023 | 26/11/2023 | A.G. ENTERPRISE | 21.49 | 2.47 | 11.48 | 15
6 | HOOGHLY | Goghat - I | Hooghly Division | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | RAGHUBATI, SUNIA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000300/2023-2024 | 2363/HUG | 08/08/2023 | 04/05/2024 | P.B. ENTERPRISE (PINTU BHADURI) | 1481.45 | 128.2 | 8.65 | 50
7 | HOOGHLY | Goghat - I | Electrical | Sunia Piped Water Supply Scheme, Block- Goghat-I, District-Hooghly | SM/18593 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sunia water supply scheme, T.W. No. III & IV, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000885/2023-2024 | 3458/ED | 11/08/2023 | 09/11/2023 | DIPALI CONSTRUCTION | 21.49 | 7.96 | 37.04 | 20
Total | [13 empty] | 1567.36 | 138.62 | 8.84