## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balundi water supply scheme, T.W. No.- I & II, Block: Aambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000912/2023-2024 | 3583/ED | 28/08/2023 | 26/11/2023 | M/S G P ENTERPRISE | 21.47 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Material Requisition To Resource Division |  |  | RTOR000411/2023-2024 | 3057/46/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 15.4 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BALUNDI PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000130/2024-2025 | 1155/ED | 14/06/2024 | 12/09/2024 | DEY ENTERPRISE | 10.75 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BALUNDI PIPED W/S SCHEME, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000131/2024-2025 | 1156/ED | 14/06/2024 | 12/09/2024 | DEY ENTERPRISE | 10.75 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Quotation of New Service Connection for Balundi w/s Scheme, PH No-III Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/18594) Application No-5004182716 Reference Id-503644451. |  |  | BILL/00448/2024-2025 | 119 | 17/05/2024 | 17/05/2024 | WBSEDCL | 4.71 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Quotation of New Service Connection for Balundi w/s Scheme,PH No-I Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18594) Application No-5004415806 Reference Id-503753690 |  |  | BILL/01985/2024-2025 | 476 | 01/10/2024 | 01/10/2024 | WBSEDCL | 8.08 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Quotation of New Service Connection for Balundi w/s Scheme, PH No-II Block-Arambag, Dist-Hooghly under Electrical Division, PHE Dte.(SM/18594) Application No-5004182766 Reference Id-503644453. |  |  | BILL/00447/2024-2025 | 121 | 17/05/2024 | 17/05/2024 | WBSEDCL | 4.54 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Quotation of New Service Connection for Balundi w/s Scheme,PH No-IV Block-Arambag,Dist-Hooghly under Electrical Division,PHE Dte.(SM/18594) Application No-5004416593 Reference Id-503753758 |  |  | BILL/01984/2024-2025 | 475 | 01/10/2024 | 01/10/2024 | WBSEDCL | 7.6 | 0 | 0 | 0
9 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 31/10/2025 | S & P ENTERPRISE | 2296.42 | 103.17 | 4.49 | 30
10 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED BALUNDI PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/18594 | New | Sinking of 3 nos 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of BULUNDI W/S Scheme under Arambagh Sub Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001532/2024-2025 | 3617/HUG | 05/11/2024 | 04/05/2025 | S & P ENTERPRISE | 48.46 | 0 | 0 | 70
Total | [13 empty] | 2428.17 | 103.17 | 4.25