## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | Material Requisition To Resource Division |  |  | RTOR000398/2023-2024 | 3057/52/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 3.38 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | Quotation Bill for New Service Connection at Selalpur W/S. Sch. TW-I |  |  | BILL/04166/2023-2024 | 400 | 09/11/2023 | 09/11/2023 | WBSEDCL | 3.98 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | Construction of 4 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 4 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 4 Nos. T.W & Distribution at SELALPUR (2Nos.), MADHABPUR (2Nos.) W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000234/2024-2025 | 3469/HUG | 04/10/2024 | 02/01/2025 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 47.22 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of SELALPUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000255/2024-2025 | 3525/HUG | 22/10/2024 | 21/11/2024 | GITA ENTERPRISE | 31.35 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SELALPUR PIPED W/S SCHEME, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000132/2024-2025 | 1157/ED | 14/06/2024 | 12/09/2024 | M/S DILIP MITRA | 10.74 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | Quotation of New Service Connection for Selalpur w/s Scheme,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/18596) Application No-5004135212, Reference Id-503626837 |  |  | BILL/00415/2024-2025 | 99 | 06/05/2024 | 06/05/2024 | WBSEDCL | 7.66 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Selalpur water supply scheme, T.W. No.- I & II, Block: Aambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000915/2023-2024 | 3586/ED | 28/08/2023 | 01/03/2025 | M/S DILIP MITRA | 21.5 | 0 | 0 | 30
8 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 31/10/2025 | S & P ENTERPRISE | 2296.42 | 0 | 0 | 30
9 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED SELALPUR PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18596 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SELALPUR PWSS - 4no's (2) TIROL PWSS (Z-I)- 4 no's (3) KUMURSA PWSS- 2no's (4) MADHABPUR PWSS- 4no's | Assistant Engineer | Junior Engineer (Civill) | ORD/002743/2024-2025 | 1151/Arg | 10/12/2024 | 10/01/2025 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 0
Total | [13 empty] | 2423.22 | 0 | 0