## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Material Requisition To Resource Division |  |  | RTOR000463/2023-2024 | 3057/19/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 20.1 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at RADHABALLAVPUR Z-I, BENGAI, SAMANTAKHANDA and BHURKUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000845/2023-2024 | 724/HUG | 05/03/2024 | 04/05/2024 | RUNA ENTERPRISE | 64.27 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Electrical | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BENGAI PIPED W/S SCHEME, T.W. No. IV, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000136/2024-2025 | 1162/ED | 14/06/2024 | 12/09/2024 | S.G. TECHNICAL SERVICES | 10.74 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Electrical | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Supply of Fuel for 1(One) no Diesel luxury Taxi on contract Carriage for the office of the Assistant Engineer Howrah mechanical Sub Division PHE Dte(JJM Work for Hooghly District) for the Month of April 2024. |  |  | BILL/00626/2024-2025 | 191 | 10/06/2024 | 10/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Quotation of New Service Connection for Bengai w/s Scheme,PH No-I Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18597) Application No-5004215163 Reference Id-503657720 |  |  | BILL/00624/2024-2025 | 186 | 03/06/2024 | 03/06/2024 | WBSEDCL | 5.66 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for Office of the Assistant Engineer-II, Electrical Division, PHE Dte. From 01.04.2024 to 30.04.2023 WB-15C-5554 |  |  | BILL/00625/2024-2025 | 187 | 03/06/2024 | 03/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
7 | HOOGHLY | Goghat-II | Electrical | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Quotation of New Service Connection for Bengai w/s Scheme, PH No-II Block-Goghat-II, Dist-Hooghly under ED,PHE Dte (SM/18597) Application No-5004034165 Reference Id-503574963 |  |  | BILL/06198/2023-2024 | 812 | 28/02/2024 | 28/02/2024 | WBSEDCL | 3.33 | 0 | 0 | 0
8 | HOOGHLY | Goghat-II | Electrical | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Quotation of New Service Connection for Bengai w/s Scheme, PH No-III Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18597) Application No-5004190291 Reference Id-503647427. |  |  | BILL/00482/2024-2025 | 150 | 22/05/2024 | 22/05/2024 | WBSEDCL | 3.24 | 0 | 0 | 0
9 | HOOGHLY | Goghat-II | Hooghly Division | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | BENGAI, SAMANTA KHANDA, BHURKUNDA (ZONE-I), BHURKUNDA (ZONE-II), SELAMPUR (ZONE-I), SELAMPUR (ZONE-II), STTANTIPUR (ZONE-I) AND SHANTIPUR (ZONE-II) piped water supply Scheme with TW, Switch room, boundary wall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at GOGHAT-II Block under ARAMBAG Sub-Division of Hooghly PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000558/2023-2024 | 3190/HUG | 31/10/2023 | 01/07/2025 | M/S PRITI ENTERPRISE | 4251.5 | 450 | 10.58 | 30
10 | HOOGHLY | Goghat-II | Electrical | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bengai water supply scheme, T.W. No.- I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000913/2023-2024 | 3584/ED | 28/08/2023 | 04/01/2025 | M.S. ENTERPRISE | 23.69 | 22.97 | 96.95 | 40
11 | HOOGHLY | Goghat-II | Electrical | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BENGAI PIPED W/S SCHEME, T.W. No. III, Block: Goghat - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000135/2024-2025 | 1161/ED | 14/06/2024 | 01/04/2025 | M.S. ENTERPRISE | 10.95 | 10.57 | 96.56 | 30
12 | HOOGHLY | Goghat-II | Hooghly Division | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Material Requisition To Resource Division |  |  | RTOR000554/2023-2024 | 178/Hug | 24/01/2025 | 24/01/2025 | Resource Division | 37.29 | 0 | 0 | 0
13 | HOOGHLY | Goghat-II | Hooghly Division | BENGAI WATER SUPPLY SCHEME | SM/18597 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Goghat- II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001930/2024-2025 | 464/HUG | 20/02/2025 | 16/01/2026 | TECHVISION | 6.59 | 0 | 0 | 30
Total | [13 empty] | 4437.84 | 483.54 | 10.9