## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-I | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Acceptance Order for NABABPUR, DUDHKALMI, HARIPUR, JAGMOHANPUR , GANGADHARPUR Piped Water Supply Scheme with.TW, Switch room, boundaryivall, rising main, LDS, FHTC & construction of RCC OHR with 20 mtr. Staging height including soil investigation work at CHANDITALA-I Block under SERAMPORE Sub-Division Under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000318/2023-2024 | 2393/HUG | 10/08/2023 | 10/08/2025 | GREEN ROYAL INFRA CON PVT LTD | 3243.22 | 370.86 | 11.43 | 9
2 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gangadharpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000919/2023-2024 | 3590/ED | 28/08/2023 | 01/03/2026 | GOENKA ENTERPRISE | 21.37 | 15.91 | 74.45 | 60
3 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Hiring of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/003200/2023-2024 | 2502_/HMSD | 26/09/2023 | 25/02/2024 | S.P. CONSTRUCTION | 0.72 | 0.43 | 59.87 | 0
4 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gangadharpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000920/2023-2024 | 3591/ED | 28/08/2023 | 01/12/2025 | M/S PS & ASSOCIATES | 20.26 | 14.32 | 70.68 | 60
5 | HOOGHLY | Chanditala-I | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Material Requisition To Resource Division |  |  | RTOR000517/2023-2024 | 3060/5/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 25.93 | 0 | 0 | 0
6 | HOOGHLY | Chanditala-I | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Material Requisition To Resource Division |  |  | RTOR000337/2023-2024 | 3005/10/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 25.89 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Gangadharpur w/s scheme,P H No 1 |  |  | BILL/04510/2023-2024 | 560 | 21/12/2023 | 21/12/2023 | WBSEDCL | 3.67 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000229/2024-2025 | 3054/HMSD | 20/06/2024 | 21/12/2024 | SIDDHARTHA CHATTERJEE. | 0.87 | 0.6 | 68.79 | 0
9 | HOOGHLY | Chanditala-I | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Construction of 200 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation at Gangadharpur Zone - II under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000302/2024-2025 | 3674/HUG | 13/11/2024 | 28/12/2024 | TOTON MONDAL | 81.06 | 0 | 0 | 0
10 | HOOGHLY | Chanditala-I | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gangadharpur (Zone-I) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001443/2023-2024 | 116/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 100
11 | HOOGHLY | Chanditala-I | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Revised Geo-reference drawing (CAD-GIS) and redesign of Network Distribution System of Gangadharpur (Zone-II) Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001444/2023-2024 | 117/SER | 23/02/2024 | 09/03/2024 | APEX ENGINEERING | 0.84 | 0.84 | 100 | 100
12 | HOOGHLY | Chanditala-I | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT GANGADHARPUR Z-I HW SITE AND Zone-II HW SITE UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000136/2024-2025 | 425/SER | 31/07/2024 | 15/08/2024 | SUNITI MAIRA | 0.68 | 0.68 | 100 | 95
13 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of December, 2023. |  |  | BILL/00837/2024-2025 | 238 | 20/06/2024 | 20/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
14 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of January,2024 |  |  | BILL/00838/2024-2025 | 233 | 20/06/2024 | 20/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
15 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Fuel consumption bill of Luxury Car / Ambassadar (BS-IV) for Official use of the Superintending Engineer, Mechanical Circle-I, PHE Dte. From:- 01/03/2024 to 31/03/2024 Bill No.- 1469 |  |  | BILL/01398/2024-2025 | 353 | 31/07/2024 | 31/07/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.25 | 0 | 0 | 0
16 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Fuel consumption bill of luxuary car / Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. Car No. WB-02AT-8617 |  |  | BILL/02302/2024-2025 | 605 | 05/12/2024 | 05/12/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.06 | 0 | 0 | 0
17 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Quotation bill for new service connection charges at Gangadharpur PWSS Zone-I, P.H. No.-II, Hooghly. Application No. 5004064346 Ref ID: 503597306 |  |  | BILL/00036/2024-2025 | 22 | 05/04/2024 | 05/04/2024 | WBSEDCL | 5.4 | 0 | 0 | 0
18 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No. WB-11C-1616 01.08.2024 to 31.08.2024 |  |  | BILL/02101/2024-2025 | 563 | 11/11/2024 | 11/11/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
19 | HOOGHLY | Chanditala-I | Hooghly Division | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | PAYMENT TO ROAD RESTORATION TO PWD JANGIPARA GANGADHARPUR ROAD |  |  | BILL/00686/2024-2025 | BP-2024-25-501 | 26/09/2024 | 26/09/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 23.35 | 0 | 0 | 0
20 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No.- WB-11C-1616 From 01.07.2024 to 31.07.2024 |  |  | BILL/01962/2024-2025 | 463 | 13/09/2024 | 13/09/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
21 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Fuel consumption bill of luxuary car/ Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. From 01.05.2024 to 31.05.2024 WB-02AT-8617 Bill No : 0239 Bill Date : 31/05/2024 |  |  | BILL/00852/2024-2025 | 253 | 24/06/2024 | 24/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0 | 0
22 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Quotation bill for new service connection charge at Gangadharpur, Zone-II, P.H. No.-II, District-Hooghly Application No.- 5004481099 Ref No.: 503803227 Scheme Code: SM/18623 |  |  | BILL/02309/2024-2025 | 611 | 05/12/2024 | 05/12/2024 | WBSEDCL | 3.85 | 0 | 0 | 0
23 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Supply of Fuel for 1(One) no Diesel driven luxury car/ Ambassadar (WB17-1864) for the Official use of the Superintending Engineer, Mechanical circle-II PHE Dte for the Month of November, 2023. |  |  | BILL/00836/2024-2025 | 237 | 20/06/2024 | 20/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.2 | 0 | 0 | 0
24 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Fuel consumption bill of luxuary car/ Ambassadar (BS-IV) for Official use of the Chief Engineer (Mechanical/ Electrical), Southern Zone, PHE Dte. From 01.04.2024 to 30.04.2024 WB-02AT-8617 Bill No : 0100 Bill Date : 30/04/2024 |  |  | BILL/00853/2024-2025 | 250 | 24/06/2024 | 24/06/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.11 | 0 | 0 | 0
25 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Quotation bill for new service connection charges at Gangadharpur w/s scheme, Zone-II, PH No.-I, Hooghly. Application No.- 5004040971 Ref ID: 503579949 |  |  | BILL/06456/2023-2024 | 885 | 15/03/2024 | 15/03/2024 | WBSEDCL | 5.59 | 0 | 0 | 0
26 | HOOGHLY | Chanditala-I | Electrical | GANGADHARPUR PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-I DISTRICT : HOOGHLY. | SM/18623 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). Car No.- WB-11C-1616 From 01.09.2024 to 30.09.2024 |  |  | BILL/02102/2024-2025 | 564 | 11/11/2024 | 11/11/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.15 | 0 | 0 | 0
Total | [13 empty] | 3465.3 | 404.49 | 11.67