## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-II | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Material Requisition To Resource Division |  |  | RTOR000477/2023-2024 | 3060/4/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 22.95 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-II | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Material Requisition To Resource Division |  |  | RTOR000382/2023-2024 | 3005/16/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 22.91 | 0 | 0 | 0
3 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | "Quotation Bill for New Service Connection at Kapasaria W/S. Sch. |  |  | BILL/02923/2023-2024 | 211 | 24/08/2023 | 24/08/2023 | WBSEDCL | 17.21 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. PH-III & IV, Z-II |  |  | BILL/04024/2023-2024 | 317 & 318 | 03/10/2023 | 03/10/2023 | WBSEDCL | 6.88 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No.- I, II, III & IV, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000918/2023-2024 | 3589/ED | 28/08/2023 | 26/11/2023 | R.N.S. TRADING | 41.38 | 38.54 | 93.14 | 90
6 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Quotation money deposition for new service connection at Kapasaria w/s scheme, Zone- I, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 100000120622 Reference ID- 860314252 SM Code- 18624 |  |  | BILL/02124/2024-2025 | 559 | 11/11/2024 | 11/11/2024 | WBSEDCL | 0.19 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. Z-II, TW-IV |  |  | BILL/04608/2023-2024 | 608 | 04/01/2024 | 04/01/2024 | WBSEDCL | 4.82 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-II | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | KAPASHARIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site at ZONE-I & Sinking of tube-well, LDS, Rising Main, FHT, Construction of switch-rooms & boundary walls at different TW site at ZONE-II, under CHANDITALA-II Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000285/2023-2024 | 2335/HUG | 07/08/2023 | 06/02/2025 | SAMIRON GHOSH | 934.14 | 592.08 | 63.38 | 10
9 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 | Assistant Engineer 1 | Junior Engineer2 | ORD/003739/2024-2025 | 331_AE-I/ED | 05/02/2025 | 31/07/2025 | SWARUP LAL SARKAR | 0.84 | 0 | 0 | 0
10 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/003095/2024-2025 | 482/ED | 18/03/2025 | 16/06/2025 | S.P. CONSTRUCTION | 11.42 | 0 | 0 | 0
11 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. IX, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/003086/2024-2025 | 480/ED | 18/03/2025 | 16/06/2025 | SWAPAN ENTERPRISE | 11.3 | 0 | 0 | 0
12 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VIII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/003090/2024-2025 | 481/ED | 18/03/2025 | 16/06/2025 | ANUPAMA ENGINEERING WORKS | 11.3 | 0 | 0 | 0
13 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Bill No. 0642 Bill Date : - 30/06/2025 |  |  | BILL/02761/2025-2026 |  | 11/09/2025 | 11/09/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
14 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. - WB-05-0982 |  |  | BILL/04788/2025-2026 |  | 10/12/2025 | 10/12/2025 | SHIVAM ENTERPRISE | 0.21 | 0 | 0 | 0
15 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. - WB-05-0982 |  |  | BILL/04789/2025-2026 |  | 10/12/2025 | 10/12/2025 | SHIVAM ENTERPRISE | 0.21 | 0 | 0 | 0
16 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB 05 0982 |  |  | BILL/04976/2025-2026 |  | 18/12/2025 | 18/12/2025 | SHIVAM ENTERPRISE | 0.03 | 0 | 0 | 0
17 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB 05 0982 Bill No. 1659 Bill Date : - 30/11/2025 |  |  | BILL/04977/2025-2026 |  | 18/12/2025 | 18/12/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
18 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No. V & VI, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000881/2023-2024 | 3454/ED | 11/08/2023 | 01/06/2026 | R.N.S. TRADING | 20.83 | 0 | 0 | 90
19 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Mobil Sl No. - 1006 Date : - 28/07/2025 |  |  | BILL/04730/2025-2026 |  | 08/12/2025 | 08/12/2025 | SWARUP LAL SARKAR | 0.03 | 0 | 0 | 0
20 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. - WB-05-0982 Bill No. 1280 Bill Date : - 30/09/2025 |  |  | BILL/04658/2025-2026 |  | 03/12/2025 | 03/12/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.04 | 0 | 0 | 0
21 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 Bill No. 0228 Bill Date : 30/04/2025 |  |  | BILL/02327/2025-2026 |  | 20/08/2025 | 20/08/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
22 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. - WB 05 0982 Bill No. - 0865 Bill Date : - 31/07/2025 |  |  | BILL/04731/2025-2026 |  | 08/12/2025 | 08/12/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
23 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 Mobil Charge |  |  | BILL/02326/2025-2026 |  | 20/08/2025 | 20/08/2025 | SWARUP LAL SARKAR | 0.03 | 0 | 0 | 0
24 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. - WB-05-0982 Bill No. 1088 Bill Date : - 31/08/2025 |  |  | BILL/04660/2025-2026 |  | 03/12/2025 | 03/12/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
25 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 Bill No. 1788 Bill Date : 31/03/2025 |  |  | BILL/00578/2025-2026 |  | 15/05/2025 | 15/05/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.22 | 0 | 0 | 0
26 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. - WB-05-0982 Bill No. 1466 Bill Date : - 31/10/2025 |  |  | BILL/04659/2025-2026 |  | 03/12/2025 | 03/12/2025 | JAMECO AGENCIES PRIVATE LIMITED. | 0.04 | 0 | 0 | 0
27 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Fuel consumption bill of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 Mobil |  |  | BILL/00577/2025-2026 |  | 15/05/2025 | 15/05/2025 | SWARUP LAL SARKAR | 0.03 | 0 | 0 | 0
Total | [13 empty] | 1108.1 | 630.62 | 56.91