## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala - II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No. V & VI, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000881/2023-2024 | 3454/ED | 11/08/2023 | 09/11/2023 | R.N.S. TRADING | 20.83 | 0 | 0 | 0
2 | HOOGHLY | Chanditala - II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | "Quotation Bill for New Service Connection at Kapasaria W/S. Sch. |  |  | BILL/02923/2023-2024 | 211 | 24/08/2023 |  | WBSEDCL | 17.21 | 0 | 0 | 0
3 | HOOGHLY | Chanditala - II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. PH-III & IV, Z-II |  |  | BILL/04024/2023-2024 | 317 & 318 | 03/10/2023 |  | WBSEDCL | 6.88 | 0 | 0 | 0
4 | HOOGHLY | Chanditala - II | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Material Requisition To Resource Division |  |  | RTOR000477/2023-2024 | 3060/4/Hug | 11/10/2023 |  | Resource Division | 22.95 | 0 | 0 | 0
5 | HOOGHLY | Chanditala - II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. Z-II, TW-IV |  |  | BILL/04608/2023-2024 | 608 | 04/01/2024 |  | WBSEDCL | 4.82 | 0 | 0 | 0
6 | HOOGHLY | Chanditala - II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No.- I, II, III & IV, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000918/2023-2024 | 3589/ED | 28/08/2023 | 26/11/2023 | R.N.S. TRADING | 41.38 | 19.27 | 46.57 | 90
7 | HOOGHLY | Chanditala - II | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | KAPASHARIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site at ZONE-I & Sinking of tube-well, LDS, Rising Main, FHT, Construction of switch-rooms & boundary walls at different TW site at ZONE-II, under CHANDITALA-II Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000285/2023-2024 | 2335/HUG | 07/08/2023 | 03/05/2024 | SAMIRON GHOSH | 934.14 | 388.58 | 41.6 | 10
Total | [13 empty] | 1048.2 | 407.86 | 38.91