## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-II | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Material Requisition To Resource Division |  |  | RTOR000477/2023-2024 | 3060/4/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 22.95 | 0 | 0 | 0
2 | HOOGHLY | Chanditala-II | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Material Requisition To Resource Division |  |  | RTOR000382/2023-2024 | 3005/16/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 22.91 | 0 | 0 | 0
3 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | "Quotation Bill for New Service Connection at Kapasaria W/S. Sch. |  |  | BILL/02923/2023-2024 | 211 | 24/08/2023 | 24/08/2023 | WBSEDCL | 17.21 | 0 | 0 | 0
4 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. PH-III & IV, Z-II |  |  | BILL/04024/2023-2024 | 317 & 318 | 03/10/2023 | 03/10/2023 | WBSEDCL | 6.88 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kapasharia water supply scheme, T.W. No.- I, II, III & IV, Block: Chanditala-II District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000918/2023-2024 | 3589/ED | 28/08/2023 | 26/11/2023 | R.N.S. TRADING | 41.38 | 38.54 | 93.14 | 90
6 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Quotation money deposition for new service connection at Kapasaria w/s scheme, Zone- I, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 100000120622 Reference ID- 860314252 SM Code- 18624 |  |  | BILL/02124/2024-2025 | 559 | 11/11/2024 | 11/11/2024 | WBSEDCL | 0.19 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Quotation Bill for New Service Connection at Kapasaria W/S. Sch. Z-II, TW-IV |  |  | BILL/04608/2023-2024 | 608 | 04/01/2024 | 04/01/2024 | WBSEDCL | 4.82 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-II | Hooghly Division | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | KAPASHARIA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site at ZONE-I & Sinking of tube-well, LDS, Rising Main, FHT, Construction of switch-rooms & boundary walls at different TW site at ZONE-II, under CHANDITALA-II Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000285/2023-2024 | 2335/HUG | 07/08/2023 | 06/02/2025 | SAMIRON GHOSH | 934.14 | 592.08 | 63.38 | 10
9 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). Car No. WB-05-0982 | Assistant Engineer 1 | Junior Engineer2 | ORD/003739/2024-2025 | 331_AE-I/ED | 05/02/2025 | 31/07/2025 | SWARUP LAL SARKAR | 0.84 | 0 | 0 | 0
10 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/003095/2024-2025 | 482/ED | 18/03/2025 | 16/06/2025 | S.P. CONSTRUCTION | 11.42 | 0 | 0 | 0
11 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. IX, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/003086/2024-2025 | 480/ED | 18/03/2025 | 16/06/2025 | SWAPAN ENTERPRISE | 11.3 | 0 | 0 | 0
12 | HOOGHLY | Chanditala-II | Electrical | KAPASHARIA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA-II DISTRICT : HOOGHLY. | SM/18624 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for KAPASARIA water supply scheme, TW No. VIII, Block: Chanditala-II, District - Hooghly under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/003090/2024-2025 | 481/ED | 18/03/2025 | 16/06/2025 | ANUPAMA ENGINEERING WORKS | 11.3 | 0 | 0 | 0
Total | [13 empty] | 1085.32 | 630.62 | 58.1