## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | ARUNDA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer |  | ORD/000290/2023-2024 | 2341/HUG | 07/08/2023 | 03/05/2024 | SIBSANKAR CHOWDHURY | 833.08 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-I) water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000925/2023-2024 | 3596/ED | 28/08/2023 | 26/11/2023 | ANJAN ENTERPRISE | 21.5 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-I) water supply scheme, T.W. No. III & IV, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000863/2023-2024 | 3435/ED | 11/08/2023 | 09/11/2023 | ANJAN ENTERPRISE | 21.5 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | Material Requisition To Resource Division |  |  | RTOR000412/2023-2024 | 3057/45/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 12.79 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HAYATPUR and ARUNDA Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000843/2023-2024 | 723/HUG | 05/03/2024 | 04/05/2024 | SPG ENTERPRISES | 64.34 | 0 | 0 | 50
6 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch room & boundary wall for ARUNDA ZONE-I Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000381/2024-2025 | 3775/HUG | 25/11/2024 | 09/01/2025 | I R CONSTRUCTION | 25.93 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS (Z-I)-1 no's (2) PURBATHAKURANICHAK PWSS (Z-I)-2 no's (3) ARUNDA PWSS (Z-I)-4 no's (4) ARUNDA PWSS (Z-II)-5 no's (5) POL PWSS-2 no's | Assistant Engineer | Junior Engineer (Civill) | ORD/002744/2024-2025 | 1152/Arg | 10/12/2024 | 10/01/2025 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
8 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SAIDPUR PWSS (Z- II) -3nos (2) BAIKUNTHAPUR PWSS- 4nos (3) DIHIBAGNAN PWSS- 3nos (4) PRATAPNAGAR PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000535/2024-2025 | 815/Arg | 23/08/2024 | 22/09/2024 | MS PRADIP KUMAR PAL | 0.98 | 0 | 0 | 100
9 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-I) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/18642 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ARANDI PWSS- 3nos (2) KAPSIT PWSS- 4nos (3) KISHORPUR PWSS- 3nos (4) DIHIBATPUR PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000534/2024-2025 | 813/Arg | 23/08/2024 | 22/09/2024 | MS PRADIP KUMAR PAL | 0.98 | 0 | 0 | 100
Total | [13 empty] | 982.08 | 0 | 0