## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | SM/18643 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Srirampur water supply scheme, Zone-I, T.W. No. I and Zone-II, T.W. No. I, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001990/2023-2024 | 118/ED | 15/01/2024 | 14/04/2024 | PRADIP KUMAR DHABAL | 21.51 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | SM/18643 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SRIRAMPUR PIPED W/S SCHEME, T.W. No. IV, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000163/2024-2025 | 1186/ED | 14/06/2024 | 12/09/2024 | SOMNATH ENTERPRISE | 10.66 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | SM/18643 | Augmentation | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of SRIRAMPUR Piped Water Supply Scheme under ARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000379/2024-2025 | 3774/HUG | 25/11/2024 | 24/01/2025 | M/S SHIVAM UDYOG | 51.47 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | SM/18643 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Srirampur T/W-II W/S scheme under Electrical Division PHE Dte. (SM/18643) |  |  | BILL/02653/2024-2025 | 637 | 18/12/2024 | 18/12/2024 | WBSEDCL | 4.17 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | SM/18643 | Augmentation | Augmentation of SRIRAMPUR Piped Water Supply Scheme with Sinking of 2 Nos. tube-well within ZONE-II, Construction of 600cum capacity RCC OHR in ZONE-II with 20.0 mtr. Staging height including soil investigation, Repairing of Existing Switch Rooms, Boundary walls at different TW sites of ZONE-I, LDS, FHTC in ZONE-I & construction of 2 Nos. switch-room & 2 Nos boundary wall, LDS, Rising Main, FHTC in ZONE-II under PURSURAH Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000289/2023-2024 | 2339/HUG | 07/08/2023 | 27/09/2025 | M/S PRADYUT KUMAR HAZRA | 812.72 | 180.61 | 22.22 | 20
6 | HOOGHLY |  | Hooghly Division | Augmentation Of Piped Water Supply Scheme For SRIRAMPUR | SM/18643 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SRIRAMPUR PWSS- 3nos (2) BACHHANARI PWSS- 3nos (3) MALAYPUR PWSS- 4nos (4) MANDRA PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002644/2024-2025 | 807/Arg | 23/08/2024 | 22/09/2024 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
Total | [13 empty] | 901.51 | 180.61 | 20.03