## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-I) water supply scheme, T.W. No. III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000876/2023-2024 | 3449/ED | 11/08/2023 | 09/11/2023 | AMIT DAS | 21.46 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Material Requisition To Resource Division |  |  | RTOR000395/2023-2024 | 3057/54/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.35 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000403/2024-2025 | 3781/HUG | 25/11/2024 | 24/01/2025 | KAJAL DEY | 55.4 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Quotation of New Service Connection for Garmandaran w/s Scheme,Zone-I,PH No-I Block-Goghat-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18646) Application No-5004423599 Reference Id-503761602 |  |  | BILL/02033/2024-2025 | 508 | 21/10/2024 | 21/10/2024 | WBSEDCL | 4.87 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Quotation of New Service Connection for Garmandaran w/s Scheme,Zone-I,PH No-II Block-Goghat-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18646) Application No-5004191479 Reference Id-503647821. |  |  | BILL/00536/2024-2025 | 179 | 30/05/2024 | 30/05/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Quotation of New Service Connection For Garmandaran w/s Scheme,Zone-I,PH No-III Block-Goghat-II Dist-Hooghly under Electrical division,PHE Dte.(SM/18646) Application No-5004431289 Reference Id-503764743 |  |  | BILL/02059/2024-2025 | 516 | 21/10/2024 | 21/10/2024 | WBSEDCL | 4.71 | 0 | 0 | 0
7 | HOOGHLY | Goghat-II | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | GARMANDARAN ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000287/2023-2024 | 2336/HUG | 07/08/2023 | 29/09/2025 | KHAN ENTERPRISE | 678.8 | 0 | 0 | 75
8 | HOOGHLY | Goghat-II | Electrical | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-I) water supply scheme, T.W. No. I & II, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000928/2023-2024 | 3599/ED | 28/08/2023 | 01/07/2025 | UNITED TRADERS | 21.47 | 0 | 0 | 40
9 | HOOGHLY | Goghat-II | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Sinking of 4 nos. tube-well by (300 X 200 mm) D.R. Rig method at SELAMPUR Z-I, SANTIPUR Z-I, SELAMPUR Z-II and GARMANDARAN Z-I Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000847/2023-2024 | 725/HUG | 05/03/2024 | 01/01/2026 | AUXILIARY TUBEWELL DRILLERS | 64.32 | 13.98 | 21.74 | 70
10 | HOOGHLY | Goghat-II | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) RAGHUBATI PWSS- 2no¿s (2) GANESHBATI PWSS- 1 no¿s (3) BENGAI PWSS- 1 no¿s (4) BHURKUNDA PWSS(Z-I)- 1no¿s (5) GARMANDARAN (Z-I)- 4 no¿s, (6) GARMANDARAN PWSS (Z-II)- 4 no¿s, (7) SAMANTAKHANDA PWSS -1 no¿s | Assistant Engineer |  | ORD/002298/2024-2025 | 1148/Arg | 10/12/2024 | 10/01/2025 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
11 | HOOGHLY | Goghat-II | Hooghly Division | Garmandaran (Zone-I) Piped Water Supply Scheme, Block- Goghat-II, District-Hooghly | SM/18646 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) KISHORPUR PWSS (ii) HARISCHAK PWSS (iii) JAGATPUR PWSS (iv) GANESHBATI PWSS (v) ARUNDA (ZONE- I) PWSS (vi) ARUNDA (ZONE- II) PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000444/2024-2025 | 803/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 876.2 | 13.98 | 1.6