## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | SM/18657 | New | Material Requisition To Resource Division |  |  | RTOR000436/2023-2024 | 3058/4/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 20.62 | 0 | 0 | 0
2 | HOOGHLY | Singur | Electrical | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | SM/18657 | New | Qoutation for new service connection at Balarambati W/S Sch., Head works Site, (T/W No - I), Dt. - Hooghly |  |  | BILL/03703/2023-2024 | 233 | 01/09/2023 | 01/09/2023 | WBSEDCL | 3.21 | 0 | 0 | 0
3 | HOOGHLY | Singur | Electrical | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | SM/18657 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Balarambati water supply scheme, T.W. No. I, II & III, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000842/2023-2024 | 3410/ED | 10/08/2023 | 08/11/2023 | ORIENTAL ENGINEERING CO. | 32.24 | 0 | 0 | 80
4 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | SM/18657 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of BALARAMBATI Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000529/2023-2024 | 3008/HUG | 05/10/2023 | 04/12/2023 | S.K ENTERPRISE | 33.79 | 0 | 0 | 100
5 | HOOGHLY | Singur | Electrical | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | SM/18657 | New | Quotation for new service connection at Balarambati W/S Sch., T/W No. - III, [SM/18657], Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503584700, Dt. - 12-03-2024, Application No. - 5004050064 |  |  | BILL/06470/2023-2024 | 894 | 18/03/2024 | 18/03/2024 | WBSEDCL | 5.07 | 0 | 0 | 0
6 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | SM/18657 | New | PAYMENT FOR ROAD RESTORATION |  |  | BILL/00265/2024-2025 | BP-2024-25-186 | 06/06/2024 | 06/06/2024 | EXECUTIVE ENGINEER HOOGHLY HIGHWAY DIVISION-II PW (ROADS) DTE. | 10.78 | 0 | 0 | 0
7 | HOOGHLY | Singur | Electrical | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | SM/18657 | New | Quotation Bill for New Service Connection at Balarambati W/S. Sch. TW-II |  |  | BILL/05924/2023-2024 | 715 | 29/01/2024 | 29/01/2024 | WBSEDCL | 6.84 | 0 | 0 | 0
8 | HOOGHLY | Singur | Hooghly Division | GROUND WATER BASED BALARAMBATI PIPED W/S SCHEME | SM/18657 | New | BALARAMBATI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block under Chandannagar Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000284/2023-2024 | 2334/HUG | 07/08/2023 | 23/06/2025 | SAMIRON GHOSH | 782.6 | 0 | 0 | 100
Total | [13 empty] | 895.16 | 0 | 0