## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-I,Chanditala-II | Hooghly Division | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | KUMIRMORA (ZONE-I & ZONE-II), PAIRAGACHA (ZONE-I & ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at CHANDITALA-I & CHANDITALA-II Block under SERAMPORE Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000299/2023-2024 | 2333/Hug | 07/08/2023 | 30/10/2025 | S & P ENTERPRISE | 964.69 | 495.38 | 51.35 | 14
2 | HOOGHLY | Chanditala-I,Chanditala-II | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-I & II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000846/2023-2024 | 3414/ED | 10/08/2023 | 08/11/2023 | S.P. CONSTRUCTION | 22.37 | 21.63 | 96.71 | 70
3 | HOOGHLY | Chanditala-I,Chanditala-II | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kumirmora water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-I & II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000845/2023-2024 | 3413/ED | 10/08/2023 | 08/11/2023 | MENAKA ENTERPRISE | 20.36 | 14.41 | 70.79 | 30
4 | HOOGHLY | Chanditala-I,Chanditala-II | Hooghly Division | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Material Requisition To Resource Division |  |  | RTOR000174/2022-2023 | 79/9Hug | 06/01/2023 | 06/01/2023 | Resource Division | 79.13 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-I,Chanditala-II | Hooghly Division | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Material Requisition To Resource Division |  |  | RTOR000520/2023-2024 | 3060/3/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 22.95 | 0 | 0 | 0
6 | HOOGHLY | Chanditala-I,Chanditala-II | Hooghly Division | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Material Requisition To Resource Division |  |  | RTOR000379/2023-2024 | 3005/3/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 85.62 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-I,Chanditala-II | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I, Z-I |  |  | BILL/04447/2023-2024 | 505 | 08/12/2023 | 08/12/2023 | WBSEDCL | 3.8 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-I,Chanditala-II | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-I, Z-II |  |  | BILL/04448/2023-2024 | 503 | 08/12/2023 | 08/12/2023 | WBSEDCL | 3.63 | 0 | 0 | 0
9 | HOOGHLY | Chanditala-I,Chanditala-II | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-II, Z-I |  |  | BILL/04450/2023-2024 | 504 | 08/12/2023 | 08/12/2023 | WBSEDCL | 3.55 | 0 | 0 | 0
10 | HOOGHLY | Chanditala-I,Chanditala-II | Electrical | KUMIRMORA PIPED WATER SUPPLY SCHEME BLOCK : CHANDITALA- I & II, DISTRICT : HOOGHLY. | SM/18666 | New | Quotation Bill for New Service Connection at Kumirmora W/S. Sch. PH-II, Z-II |  |  | BILL/04449/2023-2024 | 502 | 08/12/2023 | 08/12/2023 | WBSEDCL | 6.86 | 0 | 0 | 0
Total | [13 empty] | 1212.96 | 531.43 | 43.81