## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | KOTALPUR (ZONE-I & ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR At ZONE-I & Construction of 300 cum capacity RCC OHR At ZONE-II with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site of ZONE-I & ZONE-II under Serampore Sub-Division of Hooghly Division P.H.E Dte. Block-JANGIPARA, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000281/2023-2024 | 2321/HUG | 04/08/2023 | 01/05/2028 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 1457.97 | 364.27 | 24.98 | 45
2 | HOOGHLY | Jangipara | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kotalpur water supply scheme, Zone-II, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000847/2023-2024 | 3415/ED | 10/08/2023 | 08/11/2023 | A.S. ENTERPRISE | 20.34 | 14.41 | 70.84 | 60
3 | HOOGHLY | Jangipara | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Kotalpur water supply scheme, Zone-I, T.W. No.- I & II, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000848/2023-2024 | 3416/ED | 10/08/2023 | 08/11/2023 | P.K. ENGINEERING | 22.13 | 0 | 0 | 0
4 | HOOGHLY | Jangipara | Hooghly Division | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Material Requisition To Resource Division |  |  | RTOR000530/2023-2024 | 3060/2/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 31.37 | 0 | 0 | 0
5 | HOOGHLY | Jangipara | Hooghly Division | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Material Requisition To Resource Division |  |  | RTOR000343/2023-2024 | 3005/17/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 71.65 | 0 | 0 | 0
6 | HOOGHLY | Jangipara | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch.Z-I, PH-I |  |  | BILL/04587/2023-2024 | 596 | 29/12/2023 | 29/12/2023 | WBSEDCL | 0.74 | 0 | 0 | 0
7 | HOOGHLY | Jangipara | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch.Z-II, PH-II |  |  | BILL/04442/2023-2024 | 519A | 11/12/2023 | 11/12/2023 | WBSEDCL | 6.86 | 0 | 0 | 0
8 | HOOGHLY | Jangipara | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. |  |  | BILL/04589/2023-2024 | 597 | 29/12/2023 | 29/12/2023 | WBSEDCL | 5.03 | 0 | 0 | 0
9 | HOOGHLY | Jangipara | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. PH-I |  |  | BILL/04637/2023-2024 | 624 | 08/01/2024 | 08/01/2024 | WBSEDCL | 7.5 | 0 | 0 | 0
10 | HOOGHLY | Jangipara | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Quotation Bill for New Service Connection at Kotalpur W/S. Sch. PH-II |  |  | BILL/04636/2023-2024 | 625 | 08/01/2024 | 08/01/2024 | WBSEDCL | 5.57 | 0 | 0 | 0
11 | HOOGHLY | Jangipara | Electrical | KOTALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA DISTRICT : HOOGHLY. | SM/18667 | New | Quotation money deposition for deposit works at Kotalpur w/s scheme, Zone- I, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 100000124352 Reference ID- 860319432 SM Code- 18667 |  |  | BILL/02656/2024-2025 | 647 | 09/01/2025 | 09/01/2025 | WBSEDCL | 1.49 | 0 | 0 | 0
Total | [13 empty] | 1630.66 | 378.68 | 23.22