## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | TIROL ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site, under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000286/2023-2024 | 2338/HUG | 07/08/2023 | 01/01/2026 | MINTU CHAKRABORTY | 737.4 | 452.1 | 61.31 | 50
2 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tirol (Zone-I) water supply scheme, T.W. No. I, II & III, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000841/2023-2024 | 3409/ED | 10/08/2023 | 02/10/2025 | WEST BENGAL ENGINEERING CO. | 32.24 | 0 | 0 | 60
3 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Material Requisition To Resource Division |  |  | RTOR000465/2023-2024 | 3057/18/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.1 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Sinking of 3rd and 4th tube-well by D.R. Rig method, Construction of 2 nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary Wall at TIROL (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000786/2023-2024 | 539/HUG | 20/02/2024 | 30/03/2025 | MINTU CHAKRABORTY | 59.45 | 19.73 | 33.18 | 50
5 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000257/2024-2025 | 3530/HUG | 22/10/2024 | 06/12/2024 | PADMA ENGINEERING CO. | 47.5 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for TIROL PIPED W/S SCHEME, Zone - I, T.W. No. IV, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000133/2024-2025 | 1158/ED | 14/06/2024 | 19/02/2025 | BISALAXMI ENTERPRISE | 10.74 | 10.66 | 99.32 | 30
7 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SAIDPUR PWSS (Z- II) -3nos (2) BAIKUNTHAPUR PWSS- 4nos (3) DIHIBAGNAN PWSS- 3nos (4) PRATAPNAGAR PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000535/2024-2025 | 815/Arg | 23/08/2024 | 22/09/2024 | MS PRADIP KUMAR PAL | 0.98 | 0 | 0 | 100
8 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ARANDI PWSS- 3nos (2) KAPSIT PWSS- 4nos (3) KISHORPUR PWSS- 3nos (4) DIHIBATPUR PWSS- 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000534/2024-2025 | 813/Arg | 23/08/2024 | 22/09/2024 | MS PRADIP KUMAR PAL | 0.98 | 0 | 0 | 100
9 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) PURBA RAYPUR PWSS-2nos (2) HARADITYA PWSS-4nos (3) PALASPAI PWSS- 2nos (4) JAGATPUR PWSS- 4nos (5) BARADANGAL (Z-I)-2 nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000531/2024-2025 | 812/Arg | 23/08/2024 | 22/09/2024 | M/S KHAMRUI CONSTRUCTION | 0.98 | 0 | 0 | 100
10 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ATGHARA PWSS- 3no¿s (2) BALIPUR PWSS (ZONE-I)-4no¿s (3) GOBINDAPUR PWSS- 3no¿s (4) SHYAMPUR PWSS- 4no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/000469/2024-2025 | 806/Arg | 23/08/2024 | 22/09/2024 | MS PRADIP KUMAR PAL | 0.98 | 0 | 0 | 100
11 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) KISHORPUR PWSS (ii) HARISCHAK PWSS (iii) JAGATPUR PWSS (iv) GANESHBATI PWSS (v) ARUNDA (ZONE- I) PWSS (vi) ARUNDA (ZONE- II) PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000444/2024-2025 | 803/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
12 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) LAKSHMIPUR PWSS-4nos (2) SHYAMBALLAVPUR PWSS-3nos (3) BHANDARHATI PWSS-2nos (4) SAHAPUR PWSS-2nos (5)MAYAPUR PWSS-3nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000532/2024-2025 | 819/Arg | 23/08/2024 | 22/09/2024 | M/S KHAMRUI CONSTRUCTION | 0.98 | 0 | 0 | 100
13 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Quotation of New Service Connection for Tirol w/s Scheme,Z-I,PH No-III Block-Arambag Dist-Hooghly under Electrical Division, PHE Dte.(SM/18668) Application No-5004097240 Reference Id-503608902 |  |  | BILL/00082/2024-2025 | 37 | 09/04/2024 | 09/04/2024 | WBSEDCL | 3.72 | 0 | 0 | 0
14 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Quotation of New Service Connection for Tirol w/s Scheme,Zone-I,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/18668) Application No-5004138271, Reference Id-503628273 |  |  | BILL/00416/2024-2025 | 94 | 06/05/2024 | 06/05/2024 | WBSEDCL | 3.14 | 0 | 0 | 0
15 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-I) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/18668 | New | Quotation of New Service Connection for Tirol w/s Scheme, Zone-I, PH No-4 Block-Arambag, Dist-Hooghly Under Electrical division, PHE Dte.(SM/18668) Application No-5004256486, Reference Id-503674894. |  |  | BILL/00976/2024-2025 | 255 | 03/07/2024 | 03/07/2024 | WBSEDCL | 5.29 | 0 | 0 | 0
Total | [13 empty] | 924.43 | 482.49 | 52.19