## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/18670 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dihibatpur water supply scheme, T.W. No.- I, II & III, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000843/2023-2024 | 3411/ED | 10/08/2023 | 08/11/2023 | B.T. PROJECT PVT. LTD. | 32.89 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/18670 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Dihibatpur water supply scheme, T.W. No. IV, Block: Pursurah, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/002469/2023-2024 | 330/ED | 21/02/2024 | 21/05/2024 | AMIT DAS | 10.72 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/18670 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of DIHIBATPUR (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. |  |  | ORD/000807/2023-2024 | 597/HUG | 22/02/2024 | 22/04/2024 | AMBIAN INFRASTRUCTURE | 29.67 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/18670 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAIDPUR PIPED W/S SCHEME, T.W. No. VII, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000160/2024-2025 | 1183/ED | 14/06/2024 | 12/09/2024 | STANDARD ELECTRICALS | 10.75 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/18670 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for SAIDPUR PIPED W/S SCHEME, T.W. No. VI, Block: Pursurah, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000159/2024-2025 | 1182/ED | 14/06/2024 | 12/09/2024 | M/S CHANDIMATA ELECTRICALS | 10.73 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/18670 | Augmentation | Electric quot. of WBSEDCL for New service Connection of Dihibatpur T/W-VI W/S scheme under Electrical Division PHE Dte. (SM/18670) |  |  | BILL/01615/2024-2025 | 373 | 12/08/2024 | 12/08/2024 | WBSEDCL | 6.98 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/18670 | Augmentation | Augmentation of DIHIBATPUR Piped Water Supply Scheme with Sinking of 3 Nos. Tube Well within ZONE-I & II, Construction of 300 cum capacity RCC OHR in ZONE-I & Construction of 250 cum capacity RCC OHR in ZONE-II with 20.0 mtr. Staging height including soil investigation, Repairing of Existing Switch Rooms, Boundary walls at different TW site, LDS, Rising Main, FHTC, construction of 1 No. switch-room & boundary wall in ZONE-I & construction of 2 Nos. switch-room & 3 nos boundary wall , LDS, Rising Main, FHTC in ZONE-II under PURSURAH Block, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000288/2023-2024 | 2340/HUG | 07/08/2023 | 01/11/2025 | CONCORD ENGINEERING (ASOKE KUMAR DHAR) | 869.52 | 0 | 0 | 30
8 | HOOGHLY |  | Hooghly Division | Augmentation of Dihibatpur Piped Water Supply Scheme, Block- Pursura, District-Hooghly | SM/18670 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of SOALUK Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000814/2023-2024 | 593/HUG | 22/02/2024 | 17/04/2025 | SURAJIT SINGHA RAY | 31.57 | 0 | 0 | 98
Total | [13 empty] | 1002.83 | 0 | 0