## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-I, T.W. No. III & IV, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000871/2023-2024 | 3444/ED | 11/08/2023 | 09/11/2023 | BINAPANI ENTERPRISE | 21.38 | 0 | 0 | 0
2 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-II, T.W. No. III & IV, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000872/2023-2024 | 3445/ED | 11/08/2023 | 09/11/2023 | ASHUTOSH DAS & CO. | 20.35 | 0 | 0 | 0
3 | HOOGHLY | Tarakeswar | Hooghly Division | Baligari Piped Water Supply Scheme. | SM/18671 | New | Material Requisition To Resource Division |  |  | RTOR000434/2023-2024 | 3058/3/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 9.82 | 0 | 0 | 0
4 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-I, Z-II |  |  | BILL/04416/2023-2024 | 494 | 07/12/2023 | 07/12/2023 | WBSEDCL | 12.83 | 0 | 0 | 0
5 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Baligari water supply scheme, Zone-I, T.W. No.- I & II, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000850/2023-2024 | 3418/ED | 10/08/2023 | 08/11/2023 | BINAPANI ENTERPRISE | 21.36 | 20.72 | 96.98 | 30
6 | HOOGHLY | Tarakeswar | Hooghly Division | Baligari Piped Water Supply Scheme. | SM/18671 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for BALIGARI Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000239/2024-2025 | 3474/HUG | 04/10/2024 | 03/12/2024 | DIPTI TRADERS | 53.05 | 0 | 0 | 0
7 | HOOGHLY | Tarakeswar | Hooghly Division | Baligari Piped Water Supply Scheme. | SM/18671 | New | Construction of Boundary Wall at H/W site & Laying of Balance portion of 75 mm dia HDPE Pipe including other allied works at Talpur Mouza of Baligari water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000859/2023-2024 | 730/HUG | 05/03/2024 | 04/05/2024 | DAS CONSTRUCTION | 47.63 | 44.24 | 92.89 | 100
8 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Quotation Bill for New Service Connection at Baligori W/S. Sch. PH-I, Z-I |  |  | BILL/04646/2023-2024 | 628 | 08/01/2024 | 08/01/2024 | WBSEDCL | 9.44 | 0 | 0 | 0
9 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Quotation bill for new service connection at Baligori water supply scheme, Zone-I, P.H. No.-I, Hooghly Application No.- 100000101765 Referance ID: 860294205 |  |  | BILL/06261/2023-2024 | 860 | 11/03/2024 | 11/03/2024 | WBSEDCL | 0.47 | 0 | 0 | 0
10 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Additional quotation for effecting new service connection of Baligori Zone-II, P.H. No.-I Ref ID: 860293430 |  |  | BILL/06485/2023-2024 | 898 | 19/03/2024 | 19/03/2024 | WBSEDCL | 0.12 | 0 | 0 | 0
11 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Additional Quotation Charge for Effecting New PHE Connection at PHE-2, Baligori, Monoharpur |  |  | BILL/04853/2023-2024 | 674 | 17/01/2024 | 17/01/2024 | WBSEDCL | 1.12 | 0 | 0 | 0
12 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-II, Z-I |  |  | BILL/04643/2023-2024 | 627 | 08/01/2024 | 08/01/2024 | WBSEDCL | 4.34 | 0 | 0 | 0
13 | HOOGHLY | Tarakeswar | Electrical | Baligari Piped Water Supply Scheme. | SM/18671 | New | Quotation Bill for New Service Connection at Baligari W/S. Sch. PH-II, Z-II |  |  | BILL/04644/2023-2024 | 626 | 08/01/2024 | 08/01/2024 | WBSEDCL | 4.59 | 0 | 0 | 0
14 | HOOGHLY | Tarakeswar | Hooghly Division | Baligari Piped Water Supply Scheme. | SM/18671 | New | BALIGARI (ZONE-I & ZONE-II) Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR at ZONE-I & Construction of 300 cum capacity RCC OHR at ZONE-II with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under TARAKESWAR Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000282/2023-2024 | 2337/HUG | 07/08/2023 | 26/12/2025 | DIPTI TRADERS | 963.28 | 648.11 | 67.28 | 5
15 | HOOGHLY | Tarakeswar | Hooghly Division | Baligari Piped Water Supply Scheme. | SM/18671 | New | Sinking of1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for NANDANBATI Mouza of Baligari Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/001761/2024-2025 | 184/HUG | 24/01/2025 | 25/03/2025 | SPG ENTERPRISES | 26.58 | 0 | 0 | 0
16 | HOOGHLY | Tarakeswar | Hooghly Division | Baligari Piped Water Supply Scheme. | SM/18671 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for BAIDYAPUR mouza of Baligari Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/002388/2024-2025 | 801/HUG | 25/03/2025 | 24/05/2025 | ANALYTICA FOODTECH SERVICES PVT. LTD. | 26.48 | 0 | 0 | 0
17 | HOOGHLY | Tarakeswar | Hooghly Division | Baligari Piped Water Supply Scheme. | SM/18671 | New | Road restoration at Madpur under Baligori PWSS under Chandannagar Sub-Division P.H.E. Dte. (Part C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000307/2025-2026 | 940/CHAN | 21/07/2025 | 10/08/2025 | SARKAR CONSTRUCTION (DEBJIT SARKAR) | 4.91 | 0 | 0 | 100
Total | [13 empty] | 1227.73 | 713.07 | 58.08