## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-I | Hooghly Division | Raghubati Piped Water Supply Scheme. | SM/18672 | New | Material Requisition To Resource Division |  |  | RTOR000445/2023-2024 | 3057/27/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 10.81 | 0 | 0 | 0
2 | HOOGHLY | Goghat-I | Electrical | Raghubati Piped Water Supply Scheme. | SM/18672 | New | Quotation Bill for New Service Connection at Raghubati W/S. Sch.TW-I |  |  | BILL/04150/2023-2024 | 392 | 03/11/2023 | 03/11/2023 | WBSEDCL | 5.08 | 0 | 0 | 0
3 | HOOGHLY | Goghat-I | Hooghly Division | Raghubati Piped Water Supply Scheme. | SM/18672 | New | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for RAGHUBATI Piped Water Supply Scheme underARAMBAGH Sub Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000246/2024-2025 | 3466/HUG | 04/10/2024 | 03/12/2024 | P. B. ENTERPRISE(PINTU BHADURI) | 53.65 | 0 | 0 | 0
4 | HOOGHLY | Goghat-I | Electrical | Raghubati Piped Water Supply Scheme. | SM/18672 | New | Quotation Bill for New Service Connection at Raghubati W/S. Sch |  |  | BILL/06037/2023-2024 | 737 | 07/02/2024 | 07/02/2024 | WBSEDCL | 4.7 | 0 | 0 | 0
5 | HOOGHLY | Goghat-I | Electrical | Raghubati Piped Water Supply Scheme. | SM/18672 | New | Additional Quotation of New Service Connection for Raghubati w/S Scheme,PH No-I, Block-Goghat-I Dist-Hooghly under Electrical Division PHE Dte.(SM/18672) Application No-100000123537 Reference Id-860318457 |  |  | BILL/02307/2024-2025 | 606 | 05/12/2024 | 05/12/2024 | WBSEDCL | 0.96 | 0 | 0 | 0
6 | HOOGHLY | Goghat-I | Electrical | Raghubati Piped Water Supply Scheme. | SM/18672 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Raghubati water supply scheme, T.W. No.- I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000844/2023-2024 | 3412/ED | 10/08/2023 | 01/02/2025 | M/S NABIN GOPAL SENGUPTA | 20.36 | 5.21 | 25.57 | 50
7 | HOOGHLY | Goghat-I | Hooghly Division | Raghubati Piped Water Supply Scheme. | SM/18672 | New | RAGHUBATI, SUNIA Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at GOGHAT-I Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000300/2023-2024 | 2363/HUG | 08/08/2023 | 25/10/2025 | P.B. ENTERPRISE (PINTU BHADURI) | 1481.45 | 434.8 | 29.35 | 50
Total | [13 empty] | 1577.01 | 440.01 | 27.9