## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Augmentation of BALIPUR ZONE-I(A) Piped Water Supply Scheme with LDS, FHTC, Repairing of Existing O.H.R, Switch Rooms, Boundary walls at different TW site, under KHANAKUL-I Block, District:- Hooghly. | Assistant Engineer | Junior Engineer (Civill) | ORD/000393/2023-2024 | 2600/HUG | 29/08/2023 | 27/11/2023 | M/S R K ENTERPRISE | 267.18 | 101.47 | 37.98 | 55
2 | HOOGHLY |  | Electrical | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Balipur water supply scheme, T.W. No.- I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer3,Junior Engineer4 | ORD/000934/2023-2024 | 3613/ED | 29/08/2023 | 27/11/2023 | PURUSHOTTAM ENTERPRISE | 21.72 | 18.17 | 83.68 | 30
3 | HOOGHLY |  | Hooghly Division | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Sinking of Tube-Well, Laying Distribution System, Laying Rising Main, Providing FHTC, Construction of Switch-Rooms & Boundary Walls at different TW site For Augmentation of BALIPUR ZONE-I(B) under Arambagh SubDivision of Hooghly Division P.H.E Dte. Block- Khanakul-I, District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000388/2023-2024 | 2591/HUG | 28/08/2023 | 26/11/2023 | M/S R.M. CONSTRUCTION | 308.46 | 148.3 | 48.08 | 45
4 | HOOGHLY |  | Hooghly Division | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Augmentation of BALIPUR ZONE-II Piped Water Supply Scheme with LDS, FHTC, Repairing of Switch Rooms, Boundary walls at different TW site, under Hooghly Division P.H.E Dte.Block- KHANAKUL-I , District:- Hooghly | Assistant Engineer | Junior Engineer (Civill) | ORD/000390/2023-2024 | 2597/HUG | 29/08/2023 | 20/05/2025 | DHIRENDRA ENGINEERING & CONSTRUCTION | 172.47 | 133.75 | 77.55 | 75
5 | HOOGHLY |  | Hooghly Division | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000181/2022-2023 | 79/17/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 56.05 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Quotation of New Service Connection for Balipur w/s Scheme, Zone-I,TW No-III Block-Khanakul-I,Dist-Hooghly under Electrical Division PHE Dte. |  |  | BILL/03702/2023-2024 | 232 | 01/09/2023 | 01/09/2023 | WBSEDCL | 3.1 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Quotation of New Service Connection for Balipur w/s scheme,zone-I,TW no-3, Block-khanakul-I,Dist-Hooghly under Electrical Division PHE Dte |  |  | BILL/03885/2023-2024 | 297 | 21/09/2023 | 21/09/2023 | WBSEDCL | 10.61 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Balipur water supply scheme, T.W. No. III & IV, Block: Khanakul-I District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002470/2023-2024 | 331/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 20.85 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for AUGMENTATION Of BALIPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000125/2025-2026 | 1479/HUG | 10/06/2025 | 25/07/2025 | TANISA ENTERPRISE | 26.56 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Sinking of 2 Nos. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of 2nos. switch-room & boundary wall for Augmentation of BALIPUR Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000126/2025-2026 | 1480/HUG | 10/06/2025 | 09/08/2025 | DAS ENTERPRISE (SAMIR DAS) | 52.97 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Sinking of 1 No. Replacement tube-well at Balipur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000701/2025-2026 | 2309/HUG | 02/09/2025 | 02/10/2025 | OSMAN SEKH | 15.48 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | Augmentation of Balipur Water Supply Scheme | SM/18770 | Augmentation | Laying Balance Pipeline with ancillary work for BALIPUR Water Supply Scheme under Arambagh Sub Division of hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000123/2025-2026 | 1299/HUG | 20/05/2025 | 04/07/2025 | DHIRENDRA ENGINEERING & CONSTRUCTION | 16.28 | 0 | 0 | 75
Total | [13 empty] | 971.71 | 401.7 | 41.34