## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | Material Requisition To Resource Division |  |  | RTOR000443/2023-2024 | 3057/28/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 16.38 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Electrical | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for HIRAPUR PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000142/2024-2025 | 1168/ED | 14/06/2024 | 12/09/2024 | SRI KRISHNA NIRMAN | 10.54 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-II | Electrical | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | Quotation of New Service Connection Hirapur w/s Scheme, Zone-I,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division, PHE Dte.(SM/18771) Application No-5004008491 Reference Id-503559063 |  |  | BILL/06459/2023-2024 | 883 | 15/03/2024 | 15/03/2024 | WBSEDCL | 4.21 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Electrical | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | Quotation of New Service Connection Hirapur w/s Scheme, Zone-I,PH No-II Block-Khanakul-II Dist-Hooghly under Electrical Division, PHE Dte.(SM/18771) Application No-5004008503 Reference Id-503559062 |  |  | BILL/06458/2023-2024 | 884 | 15/03/2024 | 15/03/2024 | WBSEDCL | 8.68 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Electrical | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Hirapur water supply scheme, Zone-I, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3,Junior Engineer4 | ORD/000933/2023-2024 | 3612/ED | 29/08/2023 | 01/06/2025 | TRIO CONCERN | 17.37 | 10.61 | 61.1 | 15
6 | HOOGHLY | Khanakul-II | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) NOAPARA PWSS- 1 no¿s, (2) HAYATPUR PWSS- 2 no¿s, (3) HIRAPUR PWSS (Z-I)- 1 no¿s, (4) HIRAPUR PWSS (Z-II)- 1 no¿s (5) MAROKHANA PWSS (Z-I)- 1 no¿s, (6) MOSTAFAPUR PWSS- 2 no¿s, (7) NATIBPUR PWSS- 2 no¿s, (8) ROUTHKHANA PWSS- 1 no¿s, (9) HARISCHAK PWSS- 2 no¿s, (10) PALASPAI PWSS- 1 no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002746/2024-2025 | 1154/Arg | 10/12/2024 | 10/01/2025 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-II | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-I, CHINRA (Z-I AND II), ROUTHKHANA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000841/2023-2024 | 721/HUG | 05/03/2024 | 27/08/2025 | SPG ENTERPRISES | 64.23 | 0 | 0 | 50
8 | HOOGHLY | Khanakul-II | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 01/04/2026 | MACKINTOSH BURN LIMITED | 5743.06 | 208.21 | 3.63 | 50
9 | HOOGHLY | Khanakul-II | Hooghly Division | Hirapur (Zone-I) Piped Water Supply Scheme, Block- Khanakul-II, District-Hooghly | SM/18771 | New | Field level data validation of FHTC executed by various agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute house hold by verification through electric connection or any other unique documents and making error free database in different pipe water supply scheme under Khanakul I & II Block in the District of Hooghly under Arambagh Sub Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001929/2024-2025 | 463/HUG | 20/02/2025 | 01/01/2026 | TECHVISION | 14.8 | 0 | 0 | 20
Total | [13 empty] | 5880.24 | 218.82 | 3.72