## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Material Requisition To Resource Division |  |  | RTOR000423/2023-2024 | 3057/37/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 22.02 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000147/2024-2025 | 1170/ED | 14/06/2024 | 12/09/2024 | ANJAN ENTERPRISE | 10.71 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for CHINRA PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Khanakul - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000148/2024-2025 | 1171/ED | 14/06/2024 | 12/09/2024 | R.K.ENTERPRISE | 10.74 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Sinking of 1 No. Additional tube-well, Rising Main for inter connection between T.W & Distribution, construction of switch-room & boundary wall for CHINRA ZONE-IIPiped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000288/2024-2025 | 3669/HUG | 13/11/2024 | 28/12/2024 | MAYA CONSTRUCTION | 26.56 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Quotation money deposition for new service connection at Chingra w/s scheme, Zone- 2, T.W. No.-2, Dist.-Hooghly under PHE Dte. Application No- 5004136093 Reference ID- 503627504 SM Code- 18772 |  |  | BILL/00530/2024-2025 | 180 | 30/05/2024 | 30/05/2024 | WBSEDCL | 3.92 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Quotation of New Service Connection for Chinra w/s Scheme, Zone-II,TW No-III Block-Khanakul-II Dist-Hooghly under Electrical Division Phe Dte.(SM/18772) Application No-5004383077 Reference Id-503732160 |  |  | BILL/01928/2024-2025 | 454 | 10/09/2024 | 10/09/2024 | WBSEDCL | 3.57 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Quotation of New Service Connection for Chinra w/s Scheme,Zone-II,TW No-I Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/18772) Application No-5003988265 Reference Id-503547190 |  |  | BILL/06060/2023-2024 | 759 | 16/02/2024 | 16/02/2024 | WBSEDCL | 6.73 | 0 | 0 | 0
8 | HOOGHLY | Khanakul-II | Electrical | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Chinra water supply scheme, Zone-II, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000932/2023-2024 | 3611/ED | 29/08/2023 | 11/07/2025 | MAHADEV ENTERPRISE | 22.26 | 0 | 0 | 30
9 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | NATIBPUR, ROUTHKHANA, HIRAPUR(ZONE-I), HIRAPUR(ZONE-II) , HAYATPUR, MOSTAFAPUR, CHINRA(ZONE-I), CHTNRA( ZONE-I), MARAKHANA(ZONE-I), MARAKHANA(ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of different capacity OHR with 20 mtr. staging height including Soil Investigation work at KHANAKUL-II Block under ARAMBAGH Sub-Division of Hooghly Division PHE Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000551/2023-2024 | 3168/HUG | 19/10/2023 | 01/01/2026 | MACKINTOSH BURN LIMITED | 5743.06 | 0 | 0 | 50
10 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Sinking of 4 (Four) Nos tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at CHINRA Z-II and ARUNDA Z-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000849/2023-2024 | 726/HUG | 05/03/2024 | 06/03/2025 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 39.06 | 0 | 0 | 75
11 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) CHILADANGI PWSS- 2no's (2) PATUL PWSS -1 no's (3) RADHABALLAVPUR PWSS (Z-I)- 1 no's (4) RADHABALLAVPUR PWSS (Z-II)- 2 no's (5) UDAYPUR PWSS - 2no's, (6) UDNA PWSS - 2no's, (7) CHINRA PWSS (Z-I)- 1 no's, (8) CHINRA PWSS (Z-II)- 3 no's | Assistant Engineer | Junior Engineer (Civill) | ORD/002745/2024-2025 | 1153/Arg | 10/12/2024 | 10/01/2025 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
12 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Chinra Zone-II Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. |  |  | ORD/001574/2023-2024 | 1460/HUG | 18/05/2023 | 17/06/2023 | GLOBAL CONSTRUCTION | 11.78 | 0 | 0 | 0
13 | HOOGHLY | Khanakul-II | Hooghly Division | GROUND WATER BASED CHINRA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/18772 | New | Sinking of 4 nos. tube-well (300 X 200 mm) by D.R. Rig method at HIRAPUR Z-I, CHINRA (Z-I AND II), ROUTHKHANA Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000841/2023-2024 | 721/HUG | 05/03/2024 | 27/08/2025 | SPG ENTERPRISES | 64.23 | 0 | 0 | 50
Total | [13 empty] | 5965.62 | 0 | 0