## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Chanditala-II | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | SM/18778 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pairagacha water supply scheme, Zone-I, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000935/2023-2024 | 3614/ED | 29/08/2023 | 27/11/2023 | M/S P.P. ELECTRICALS | 20.34 | 16.06 | 78.94 | 40
2 | HOOGHLY | Chanditala-II | Hooghly Division | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | SM/18778 | New | KUMIRMORA (ZONE-I & ZONE-II), PAIRAGACHA (ZONE-I & ZONE-II) Piped Water Supply Scheme with T.W, SWITCH ROOM, BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at CHANDITALA-I & CHANDITALA-II Block under SERAMPORE Sub-Division of Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000395/2023-2024 | 2601/HUG | 29/08/2023 | 18/11/2025 | S & P ENTERPRISE | 917.75 | 91.79 | 10 | 40
3 | HOOGHLY | Chanditala-II | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | SM/18778 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Pairagacha water supply scheme, Zone-II, T.W. No.- I & II, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000936/2023-2024 | 3615/ED | 29/08/2023 | 27/11/2023 | INDRANI ENTERPRISE | 20.27 | 0 | 0 | 40
4 | HOOGHLY | Chanditala-II | Hooghly Division | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | SM/18778 | New | Material Requisition To Resource Division |  |  | RTOR000500/2023-2024 | 3060/1/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 19.2 | 0 | 0 | 0
5 | HOOGHLY | Chanditala-II | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | SM/18778 | New | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone-II, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 5004303896 Reference ID- 503696996 SM Code- 18778 |  |  | BILL/01404/2024-2025 | 348 | 31/07/2024 | 31/07/2024 | WBSEDCL | 3.68 | 0 | 0 | 0
6 | HOOGHLY | Chanditala-II | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | SM/18778 | New | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone-II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004303977 Reference ID- 503697862 SM Code- 18778 |  |  | BILL/01405/2024-2025 | 346 | 31/07/2024 | 31/07/2024 | WBSEDCL | 3.53 | 0 | 0 | 0
7 | HOOGHLY | Chanditala-II | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | SM/18778 | New | Quotation money deposition for new service connection at Pairagacha w/s scheme, Zone- I, T.W. NO- I, Dist.-Hooghly under PHE Dte. Application No- 5004091751 Reference ID- 503606734 SM Code- 18778 |  |  | BILL/00160/2024-2025 | 69 | 16/04/2024 | 16/04/2024 | WBSEDCL | 4.86 | 0 | 0 | 0
8 | HOOGHLY | Chanditala-II | Electrical | PAIRAGACHA PIPED WATER SUPPLY SCHEME BLOCK: CHANDITALA-II DISTRICT: HOOGHLY. | SM/18778 | New | Quotation money deposition for deposit works at Piaragacha w/s scheme, Zone- II, T.W. No.-I, Dist.-Hooghly under PHE Dte. Application No- 100000126265 Reference ID- 860320585 SM Code- 18778 |  |  | BILL/02856/2024-2025 | 671 | 21/01/2025 | 21/01/2025 | WBSEDCL | 8.77 | 0 | 0 | 0
Total | [13 empty] | 998.39 | 107.85 | 10.8