## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | SM/18791 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1107/5/HUG | 17/04/2023 | 17/04/2023 | Resource Division | 3.08 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | SM/18791 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for PANCHGHORA PIPED W/S SCHEME, T.W. No. IV, Block: Chanditala-II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002577/2023-2024 | 453/ED | 05/03/2024 | 03/06/2024 | D. K. ELECTRIC | 9.7 | 0 | 0 | 65
3 | HOOGHLY |  | Electrical | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | SM/18791 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Panchghora water supply scheme, T.W. No. I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000993/2023-2024 | 3789/ED | 26/09/2023 | 25/12/2023 | SRI KRISHNA NIRMAN | 10.74 | 0 | 0 | 80
4 | HOOGHLY |  | Electrical | Source Augmentation of Panchghora W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | SM/18791 | Augmentation | Quotation bill for new service connection charges at Panchghara PWSS P.H. No.-IV, Hooghly. Application No. 5004090927 Ref ID: 503606723 |  |  | BILL/00486/2024-2025 | 148 | 22/05/2024 | 22/05/2024 | WBSEDCL | 3.48 | 0 | 0 | 0
Total | [13 empty] | 27 | 0 | 0