## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Improvement of ¿MEGHSAR¿ Piped Water Supply Scheme by laying of HDPE Pipeline by HDD Process & Open cut method including restoration work at Mahanad Bandel Road within Meghsar PWSS under Chinsurah Sub Division. | SM/18926 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Jatarpur village under Polba Dadpur Block, Tarabehari village of Polba Dadpur Block and Goai village of Polba Dadpur Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000997/2023-2024 | 271/CH | 14/03/2024 | 21/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.48 | 50 | 100
Total | [13 empty] | 0.95 | 0.48 | 50