## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18928 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at BHANDARHATI (1NO.), PURBA THAKURANI CHAK (2NOS.), HARISH CHAK (2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer |  | ORD/000591/2023-2024 | 3268/HUG | 08/11/2023 | 07/01/2024 | KRISHNA MONDAL | 58.98 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18928 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BHANDARHATI (1NO.),PURBA THAKURANI CHAK( 2NOS.), HARISH CHAK( 2NOS.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000644/2023-2024 | 3474/HUG | 29/11/2023 | 13/01/2024 | CIVIL CRAFT | 88.67 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18928 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of PURBA THAKURANICHAK ZONE-II PWSS under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000104/2023-2024 | 1424/HUG | 17/05/2023 | 01/07/2023 | RANA ENTERPRISE | 23.85 | 20.43 | 85.64 | 100
4 | HOOGHLY |  | Electrical | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18928 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for PURBA THAKURANICHAK PIPED W/S SCHEME, T.W. No. III & IV, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000372/2024-2025 | 1455/ED | 25/07/2024 | 23/10/2024 | M.S. ENTERPRISE | 22.21 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18928 | Augmentation | Protection works and other allied works at Head Work Site of PURBA THAKURANICHAK under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000467/2024-2025 | 4049/HUG | 19/12/2024 | 19/03/2025 | M/S. R. M. CONSTRUCTION | 23.91 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18928 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) PATUL PWSS (ii) GHOSHPUR PWSS (iii) UDNA PWSS (iv) POLE PWSS (v) GOBINDAPUR PWSS (vi) THAKURANICHAK PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000436/2024-2025 | 800/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
7 | HOOGHLY |  | Electrical | Improvement of PURBA THAKURANICHAK Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18928 | Augmentation | Quotation for New Service connection at Purba Thakuranichak Z1 ph no-3 in Khanakul-I Block SM/18928 |  |  | BILL/00379/2025-2026 |  | 29/04/2025 | 29/04/2025 | WBSEDCL | 9.06 | 0 | 0 | 0
Total | [13 empty] | 227.63 | 20.43 | 8.97