## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at HARADITYA (2Nos.),GOURHATI (2Nos.),MAINAN (1No.)W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000646/2023-2024 | 3476/HUG | 29/11/2023 | 13/01/2024 | SPG ENTERPRISES | 87.88 | 0 | 0 | 20
2 | HOOGHLY |  | Electrical | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for MAINAN PIPED W/S SCHEME, T.W. No. III & IV, Block: Khanakul-I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000370/2024-2025 | 1454/ED | 25/07/2024 | 23/10/2024 | SUDIKSHA CONSTRUCTION | 22.11 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Protection works and other allied works at Head Work Site of MAINAN Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte |  |  | ORD/000475/2024-2025 | 4054/HUG | 19/12/2024 | 19/03/2025 | DILIP KUMAR GHOSH | 22.94 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of MAINAN PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000446/2024-2025 | 4085/HUG | 19/12/2024 | 19/03/2025 | M/S S & P CONSTRUCTION | 11.13 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Providing 1200 nos Functional Household Tap Connection (FHTC) within the command area of Mainan Water Supply Scheme at Mainan Mouza under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer |  | ORD/000299/2021-2022 | 2210/Hug | 14/12/2021 | 12/02/2022 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 56 | 0 | 0 | 95
6 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Construction of 3.6 m X 3.00 m Switch Room with Additional Plinth Height, without Sanitary and Water Supply arrangement at 3rd TW Site of DIHI BAGNAN W/S Scheme under Arambag Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000428/2021-2022 | 53/Arg | 31/01/2022 | 17/03/2022 | ANNAPURNA CONSTRUCTION | 3.54 | 0 | 0 | 95
7 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Laying of pipe line for left out portion within command area of Bhunia Para, Dakshin Khan Para, Das Para, Ghorui Para, Mainan Pry School habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-A) | Assistant Engineer |  | ORD/000362/2022-2023 | 608/Arg | 31/08/2022 | 30/09/2022 | NIRMAN ENGINEERS CO - OPERATIVE SOCIETY LTD. | 4.92 | 0 | 0 | 95
8 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Laying of pipe line for left out portion within command area of Maity Para, Maj Mahissya Para, Mallik Para, Mete Para habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-B) | Assistant Engineer |  | ORD/000363/2022-2023 | 609/Arg | 31/08/2022 | 30/09/2022 | SARADA ENGINEERS CO OPERATIVE AND CONSTRUCTION SOCIETY LTD. | 4.9 | 0 | 0 | 95
9 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Laying of pipe line for left out portion within command area of Paschim Bha Para, Sk Para, Uttar Bera Para, Uttar Khan Para habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-D) | Assistant Engineer |  | ORD/000367/2022-2023 | 611/Arg | 31/08/2022 | 30/09/2022 | SUSANTA KUMAR | 4.75 | 0 | 0 | 95
10 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Laying of pipe line for left out portion within command area of Middya Para, Panchtik Middya Para, Panja Para, Paschim Bandh habitation of Mainan Village under MAINAN Water Supply Scheme to facilate the FHTC under JALASWAPNA Programme of Arambagh Sub-Division, P.H.E. Dte., Dist-. Hooghly. [Block-Khanakul-I]. (Part-C) | Assistant Engineer |  | ORD/000366/2022-2023 | 610/Arg | 31/08/2022 | 30/09/2022 | R.S. CONSTRUCTION & CONSULTANCY | 4.9 | 0 | 0 | 95
11 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at MAINAN(1No.),CHIKRAND ZONE-I (1No.),CHIKRAND ZONE-II (1No.) ,CHANDITALA (2NOS.) W/S Scheme under Hooghly Division, P.H.E. Dte.(SOURCE AUGMENTATION) | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000622/2023-2024 | 3388/HUG | 22/11/2023 | 06/01/2024 | SPG ENTERPRISES | 87.88 | 0 | 0 | 100
12 | HOOGHLY |  | Electrical | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Quotation of New Service Connection for Mainan w/s Scheme,PH No-4 Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/18929) Application No-5004288912 Reference Id-503688427. |  |  | BILL/01158/2024-2025 | 293 | 15/07/2024 | 15/07/2024 | WBSEDCL | 7.06 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Quotation of New Service Connection for Mainan w/s Scheme,PH No-III Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/18929) Application No-5004320142 Reference Id- 503705441 |  |  | BILL/01376/2024-2025 | 336 | 30/07/2024 | 30/07/2024 | WBSEDCL | 8.26 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Improvement of MAINAN Piped Water Supply Scheme to provide FHTC within uncovered villages under Command Area of the Scheme Block- Khanakul-I | SM/18929 | Augmentation | Construction of 6 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at HARADITYA (2Nos.), GOURHATI (2Nos.), MAINAN (2Nos.) W/S Scheme under ARAMBAGH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer | Junior Engineer (Civill) | ORD/000597/2023-2024 | 3312/HUG | 10/11/2023 | 09/05/2025 | DILIP KUMAR GHOSH | 70.72 | 0 | 0 | 32
Total | [13 empty] | 396.99 | 0 | 0