## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18932 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000576/2023-2024 | 3234/HUG | 06/11/2023 | 05/01/2024 | RAJDEEP CONSTRUCTION | 59 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18932 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000610/2023-2024 | 3357/HUG | 21/11/2023 | 19/02/2024 | B.K ENTERPRISE | 88.58 | 14.86 | 16.77 | 60
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18932 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001205/2023-2024 | 4483/ED | 23/11/2023 | 21/02/2024 | M/S A.K BANERJEE | 21.49 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18932 | Augmentation | Special Repairing, maintenance work of damaged R.C.C. Elevated Resovoir, Switch Room & Boundary wall of SRIPUR BALAGARH Water Supply Scheme under Chinsurah Sub - Division, P.H.E. Dte., Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000309/2024-2025 | 3678/HUG | 13/11/2024 | 22/04/2025 | DIPTI TRADERS | 29.54 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SRIPUR BALAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18932 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under BALAGARH Block of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000268/2024-2025 | 927/CH | 05/11/2024 | 10/11/2024 | MAA BUNAMATA ENTERPRISE | 3.7 | 0.98 | 26.48 | 90
Total | [13 empty] | 202.32 | 15.84 | 7.83