## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18934 | Augmentation | Construction of 5 Nos. 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , 5 Nos. Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between 5 Nos. T.W & Distribution at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000576/2023-2024 | 3234/HUG | 06/11/2023 | 05/01/2024 | RAJDEEP CONSTRUCTION | 59 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18934 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at SRIPUR BALAGARH (1No.), NATUNCHAR KRISHNABATI (2Nos.), ITAGARH (2Nos.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000610/2023-2024 | 3357/HUG | 21/11/2023 | 19/02/2024 | B.K ENTERPRISE | 88.58 | 28.58 | 32.26 | 60
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18934 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME Block- Balagarh, District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001207/2023-2024 | 4485/ED | 23/11/2023 | 01/01/2026 | BARISAL TRADING CO. | 21.49 | 0 | 0 | 25
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18934 | Augmentation | Quotation for new service connection for source Augmentation of ITAGARH Water Supply Scheme, TW NO- IV in the district Hooghly under Electrical Division, PHE Dte. ( SM/18934), Reference Id- 503795724 Application no- 5004470487 |  |  | BILL/02293/2024-2025 | BP-24-25-594 | 21/11/2024 | 21/11/2024 | WBSEDCL | 7.02 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18934 | Augmentation | Quotation for new service connection for source Augmentation of ITAGARH Water Supply Scheme, PH NO- III in the district Hooghly under Electrical Division,PHEDte. ( SM/18934), Reference Id- 503814971 Application no- 5004498167 |  |  | BILL/02600/2024-2025 | 631 | 18/12/2024 | 18/12/2024 | WBSEDCL | 6.54 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18934 | Augmentation | Repairing & Renovation of boundary wall and Land Development at H/W Site of Itagarh Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/002005/2024-2025 | 289/CH | 20/02/2025 | 02/03/2025 | TAPAS ADHYA | 4.29 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF ITAGARH PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18934 | Augmentation | Repairing & Renovation of Switch Room and Store Room at H/W Site of Itagarh Water Supply Scheme Under Balagarh Block of Chinsurah Sub-Division Under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/002006/2024-2025 | 290/CH | 20/02/2025 | 02/03/2025 | TAPAS ADHYA | 3.17 | 0 | 0 | 0
Total | [13 empty] | 190.09 | 28.58 | 15.03