## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18935 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000577/2023-2024 | 3235/HUG | 06/11/2023 | 05/01/2024 | EVERGREEN TRADERS | 59.68 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18935 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME Block- Balagarh District- Hooghly under JJM Program under Electrical Division PHE Dte. |  |  | ORD/001208/2023-2024 | 4486/ED | 23/11/2023 | 21/02/2024 | CINZANO | 21.5 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18935 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000612/2023-2024 | 3358/HUG | 21/11/2023 | 05/01/2024 | ACME CONSTRUCTION | 87.88 | 0 | 0 | 60
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18935 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly 2 Nos of Musuria village under Balagrh Block, Akna village of Chinsurah Magra Block and Benabharui village of Chinsurah Magra Block under Chinsurah Sub Division of Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000984/2023-2024 | 258/CH | 14/03/2024 | 21/03/2024 | R.K. TRADERS | 0.95 | 0 | 0 | 100
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18935 | Augmentation | Quotation for new service connection for source Augmentation of EKTARPUR Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18935), Reference Id- 503777877 Application no- 5004449206 |  |  | BILL/02273/2024-2025 | BP-24-25-581 | 19/11/2024 | 19/11/2024 | WBSEDCL | 11.08 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF EKTARPUR PIPED W/S SCHEME UNDER BALAGARH BLOCK | SM/18935 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at 2nd TW Site (PH-2) of Ektarpur PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at BALAGARH Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001853/2024-2025 | 232/CH | 19/02/2025 | 16/03/2025 | MAA BUNAMATA ENTERPRISE | 2.99 | 0 | 0 | 100
Total | [13 empty] | 184.09 | 0 | 0