## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18936 | Augmentation | Construction of 5 Nos.3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, 5 Nos. Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between 5 Nos.T.W & Distribution at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) |  | ORD/000577/2023-2024 | 3235/HUG | 06/11/2023 | 05/01/2024 | EVERGREEN TRADERS | 59.68 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18936 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 240 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at EKTARPUR (2Nos.), BELUN (2Nos.), CHOPA (1No.) W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte. (SOURCE AUGMENTATION) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000612/2023-2024 | 3358/HUG | 21/11/2023 | 05/01/2024 | ACME CONSTRUCTION | 87.88 | 0 | 0 | 60
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18936 | Augmentation | Quotation for new service connection for source Augmentation of BELUN Water Supply Scheme, TW NO- III in the district Hooghly under Electrical Division, PHE Dte. ( SM/18936 ), Reference Id- 503802585 Application no- 5004479701 |  |  | BILL/02529/2024-2025 | 613 | 05/12/2024 | 05/12/2024 | WBSEDCL | 5.48 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18936 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME Block- Pandua District- Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/001209/2023-2024 | 4487/ED | 23/11/2023 | 01/11/2025 | C.M.S. ENGINEERING CONCERN | 21.64 | 0 | 0 | 50
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18936 | Augmentation | Repairing & Renovation of boundary wall and Land development at H/W Site of Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001858/2024-2025 | 237/CH | 19/02/2025 | 01/03/2025 | TOTON MONDAL | 4.6 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18936 | Augmentation | Repairing & Renovation of Switch room and Store Room at H/W Site Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001906/2024-2025 | 256/CH | 20/02/2025 | 02/03/2025 | JOY GURU ENTERPRISE | 3.06 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BELUN PIPED W/S SCHEME UNDER PANDUA BLOCK | SM/18936 | Augmentation | Repairing & Renovation of boundary wall , Switch room and Land development at PH-2 of Belun PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte at PANDUA Block | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001907/2024-2025 | 257/CH | 20/02/2025 | 02/03/2025 | TOTON MONDAL | 2.58 | 0 | 0 | 100
Total | [13 empty] | 184.92 | 0 | 0